## Architecture
REFM Platform: Architecture Reference
Locked decisions. Every prompt must comply with these. Version 2 (supersedes Modeling_Hub_Prompt.xlsx)
1. DATA HIERARCHY
Layers | 5 layers: Master Holding → Sub-Project (Fund) → Phase → Asset → Sub-Unit. Single-project users leave Master Holding null. Sub-Project = a fund / zone / standalone project. Phase = sequenced timeline chunk within a Sub-Project. Asset = building or operating entity. Sub-Unit = saleable/operable inventory within an asset.
Master Holding | Optional top-level entity owning master land, takes revenue share % from each Sub-Project, carries master debt for land acquisition. Has its own P&L, cashflow, returns. When present, Sub-Projects contribute equity (cash + land in-kind), pay revenue share, and roll up to Master Holding consolidation.
Sub-Project (Fund) | Independent financing unit. Has its own equity stack (cash + land in-kind), debt, scenarios, returns (FCFE IRR, DDM IRR, MOIC). Can have one or many Phases. Can stand alone (no Master Holding) or be part of a Master Holding.
Phase | Sequenced chunk with own Construction Start / Operations Start / Handover. Multiple Phases can overlap. Each Phase has its own capex curve, can have its own asset list. Phase-level financing is permitted but optional (most cases finance at Sub-Project level).
Asset | Building or operating entity. Has type (locked enum from list of 20, see section 2), category (Sell/Operate/Lease/Hybrid - drives form rendering), one or more Sub-Units. Has own land allocation, capex stack (9 categories), revenue stream(s).
Sub-Unit | Inventory unit. For Sell mode: 1BR/2BR/Studio/Branded Suite/Villa V1/V2 etc. For Operate mode: Twin Key/King Key/Suite. For Lease mode: optional split by floor or zone. Each Sub-Unit has area, count, price/rate, and may have its own pricing escalation.
Securitization | OUT OF SCOPE for v1. Not modeled. Defer to v2.
2. ASSET TYPE CATALOG
Pre-built types (20) | Sell category: Branded Villas, Branded Apartments, High-end Villas, High-end Apartments, Class B Apartments. Operate category: Hotel 4-star, Hotel 5-star, Resort, Serviced Apartments, Senior Living, Student Housing. Lease category: Retail, Office, Industrial, Healthcare, Self-Storage, Data Center. Mixed/Special: Marina, Cinema, Mixed-Use.
Custom types | User can add custom asset types. Required fields: name (string), category (dropdown: Sell / Operate / Lease / Hybrid). Category drives form rendering, Sell shows units × price form, Operate shows occupancy × ADR form, Lease shows area × rate form, Hybrid shows multiple stream forms.
Category enum | Sell, Operate, Lease, Hybrid. Locked. Hybrid asset can have 2+ revenue streams (e.g., serviced apartments selling AND operating same units; mixed-use building leasing podium and operating hotel floors). Each stream is configured separately within the Hybrid asset.
Type → P&L mapping | Sell types use revenue recognition + receivables roll-forward. Operate types use full Uniform System of Accounts P&L (see section 6). Lease types use NOI = Revenue − OpEx. Hybrid types compose multiple.
3. CURRENCY
Single currency per project | v1 limitation. Set at Sub-Project creation. All values in that currency. Master Holding currency = Sub-Projects currency (must match).
Multi-currency | DEFERRED to v2.
4. SCENARIO SYSTEM
Three primary scenarios | Base / Management / Upside. Each is a named scenario stored as a delta over Base assumptions for: occupancy curves, ADR growth, sale velocity, down payment %, escalation, payment plan installments, rental growth, vacancy.
Additional scenarios | User can add unlimited additional named scenarios. UI surfaces the 3 primaries by default; user accesses extras via a 'More scenarios' menu.
Active scenario | Toggle in Topbar drives display. All KPIs, charts, exports reflect active scenario.
Sensitivity inputs | Per scenario, user can override: occupancy %, ADR growth %, ADR base, sale velocity (units sold per year curve), down payment %, escalation %, payment plan installments, rental growth %, vacancy %. Other inputs inherit from Base.
Final Dashboard scenario toggle | Module 11 dashboard has live scenario switcher. KPIs, charts, returns refresh on toggle without reload.
5. FINANCING STRUCTURE
Tranches | Up to 3 financing tranches per Sub-Project, with seniority order (1=most senior). Each tranche has: name, principal amount or % of capex, term, interest rate (fixed only for v1), drawdown schedule (linear / s-curve / custom %), repayment method (fixed / cash sweep / balloon), repayment start period. Standard pattern: Senior + Mezzanine + Equity.
Equity composition | Equity = Cash + Land In-kind. Both contribute to equity stack. Land in-kind value uses Land Value × parcel allocation. Cash equity drawdowns scheduled separately.
Interest | Fixed rate per tranche for v1. Floating (SAIBOR + premium) deferred to v2. Interest During Construction capitalizes per tranche toggle. Half-period interest convention on drawdowns.
Master Fund debt | If Master Holding exists, it can carry its own debt (typically for land acquisition) separate from Sub-Project debt. Master Holding interest expensed against Master Holding revenue share.
DSCR / ICR | Calculated and displayed per period. DSCR < 1.2x flagged amber, < 1.0x flagged red. Used for monitoring, not for sizing in v1.
Securitization | OUT OF SCOPE.
6. HOSPITALITY P&L (Uniform System of Accounts for the Lodging Industry, USAH)
Revenue | Departmental: Rooms (Occupied Nights × ADR), F&B (% of Rooms or Occupied × Guests/Room × Spend/Guest), Spa/Health Club (% of Rooms), Other (% of Rooms). ADR Growth Rate per year (compounding).
Departmental Expenses | Per department as % of departmental revenue. Defaults: Rooms 15-25%, F&B 50-60%, Spa 50%, Other 40%. User configurable per asset.
Departmental Income | Departmental Revenue − Departmental Expenses.
Undistributed Operating Expenses | % of total revenue: A&G (Admin & General), Group Services, Marketing/Sales, POM (Property Ops & Maintenance), Utilities. User configurable per asset.
Gross Operating Profit (GOP) | Departmental Income − Undistributed.
Base Management Fee | % of total revenue. User configurable. Defaults vary 1.5-3%.
Adjusted GOP | GOP − Base Management Fee.
Fixed Expenses | Incentive Management Fee (% of Adjusted GOP), Insurance (% of revenue), Replacement Reserve / FF&E Reserve (% of revenue), Property Tax / Land Lease (if applicable).
EBITDA after FF&E Reserve | Final operating output. Reported with PAR (per available room) and POR (per occupied room) KPIs.
Land Lease | Optional toggle per asset. Deducted as separate line above EBITDA when active. Has own growth rate.
7. REVENUE MODES (3 modes + hybrid)
SELL mode | Inventory: Sub-Units × Price/Unit OR Area sqm × Price/sqm. Indexation factor compounding annually. Pre-sale velocity schedule (% sold per year, sums to ≤100%). Down Payment % per year. Payment plan after DP (installments over N years). Cash collection profile per cohort (2D matrix: Year-N sales generate collections in Year N, N+1, N+2 per installment schedule). Revenue Recognition profile separate from cash collection (over construction period). Sales During Operation (residual unsold sold post-handover at indexed price). Receivables Roll-Forward: Opening + New Sales − Collected = Closing. Sales Commission % deducted from revenue.
OPERATE mode (full USAH per section 6) | Inventory: Keys/Units × Days/Year × Occupancy %. Revenue: Occupied × ADR. F&B/Spa/Other as % of Rooms. Operations Start Year per asset (not project-level). Multi-scenario occupancy curves.
LEASE mode | Inventory: Total Lease Area sqm. Loading factor: Gross × (1−Loading%) = Rentable. Vacancy %: Rentable × (1−Vacancy) = Leased. Revenue = Leased × Rent SAR/sqm/year. Rental Growth Rate compounding. OpEx % of revenue (or itemized). NOI = Revenue − OpEx.
HYBRID mode | Asset has 2+ revenue streams running simultaneously. Common case: serviced apartments (Sell + Operate same units, sold post-handover). Mixed-use building (Lease podium + Operate hotel floors). Each stream configured separately, all roll up to single asset P&L.
8. CAPEX STACK (per Asset)
9 line categories | 1. Land Cost (parcel area × rate × active flag). 2. Hard Construction (broken by Sub-Unit, sqm × rate or per-key). 3. Construction Parking (Parking sqm × rate). 4. Infrastructure (Land sqm × % × rate). 5. Landscaping (Land sqm × % × rate). 6. Pre-operating (% of Hard + Infra + Landscape). 7. Professional Fee (% of Hard + Parking). 8. Commission (% of Pre-sale + Post-operation revenue, creates loop). 9. Contingency (% of Hard + Parking).
Capex phasing | Each cost category has its own % allocation across construction periods, summing to 100%. Standard patterns: Land 100% Y1, Hard 30/30/30/10 over 4 years, Pre-op spread per asset operations curve, Commission tied to revenue schedule.
Cost methods | fixed, rate_total_allocated, rate_net_developable, rate_roads, rate_gfa, rate_bua, percent_base (loops over selectedIds), percent_total_land, percent_cash_land, percent_inkind_land. Existing Module 1 supports these, preserve.
Project-scope vs asset-scope | Cost item has scope='asset' (belongs to one asset) or scope='project' (allocated across assets via direct_cost share or gfa share). Existing Module 1 V14, preserve.
Dev Fee circular | When devFeeMode='include', dev fee total = base × rate / (1 − rate). Existing V14 logic, preserve.
9. AI AGENTS
Research agent | Pulls market intel for a city: population, demographics, GDP, key sectors, infrastructure, transport, regulations. Anthropic SDK + web search tool. Cached per city for 7 days.
Market Rates agent | Pulls current ADR / RevPAR / Cap Rates / Rental rates / Construction costs by (city, asset_type) pair. Anthropic SDK + web search tool. Cached per (city, asset_type) for 7 days.
User override | Every agent-suggested value has user override input. User-set values take priority. Agent values are suggestions stored separately for audit.
Cost control | Cache aggressively. Single agent run per (key, day) per user. Display 'Last refreshed N days ago' with manual refresh button.
10. EXPORT
Excel Static | Token-driven exceljs. FAST color convention (blue inputs / black formulas / green cross-sheet / red external / yellow assumptions). Built. Phase 2 of design tokens shipped.
Excel Formula | Full formula-driven workbook with named ranges, XIRR/XNPV, scenario switches via INDIRECT, sensitivity tables. Enterprise tier. Build in Module 13.
PDF Basic | @react-pdf/renderer. Token-driven. Built. Phase 3 shipped.
PDF Whitelabel | Per-client branded PDF (logo, color override, custom footer). Enterprise tier. Build in Module 13.
Investment Memorandum (PDF + PPT) | Module 12. Sections: Cover, Exec Summary, Highlights, Market, Location, Project Description, Development Program, Financial Summary, Investment Structure, Comparables, Risks, Macro, Developer Profile. PDF + PPT formats. v1 only static export, in-app interactive view deferred.
11. FINAL DASHBOARD (Module 11)
Purpose | Project home screen with live KPIs, charts, scenario switcher. Becomes the default view after Module 1 setup is complete.
KPIs | IRR (FCFE + DDM), MOIC, NPV at user-set discount rate, Payback Year, Development Margin %, Profit on Cost %, Cash-on-Cash, DSCR average, LTC, LTV, Equity Multiple.
Charts | Cashflow waterfall (capex → revenue → debt service → equity returns), Sources & Uses bar, Returns by year line, Sensitivity tornado, Breakeven occupancy chart, Capital stack pie, Distribution timeline.
Scenario switcher | Top-of-page toggle for Base / Management / Upside / Custom. All metrics + charts refresh live.
Sensitivity tables | NPV vs discount rate, IRR vs occupancy, IRR vs sale price, IRR vs ADR. 2D tables with conditional formatting.
Breakeven analysis | Per asset: occupancy that breaks even on EBITDA / Interest / Debt Service. For Sell: sale price that breaks even on equity invested.
12. DESIGN TOKENS & FAST CONVENTION (locked from Phase 1-4)
Token system | src/hubs/modeling/design-tokens/. Universal across all platforms. Pulled from CMS header_settings.brand_color (currently #1E3A8A navy) for chrome. FAST cells encoded as semantic tokens.
FAST cell rules | Inputs: blue text on white background (--color-navy-pale + --color-navy). Formulas: black text on light grey (--color-grey-pale + --color-heading). Linked: green text. External: red text. Assumptions: yellow background. ABSOLUTE: no hardcoded hex anywhere outside token files.
Cell primitives | InputCell, FormulaCell, LinkedCell, AssumptionCell, SectionHeader, KpiCard, TableHeader. Use these, do not write inline styles.
Light + Dark mode | All components must work in both. Light = white surfaces. Dark = navy-tinted surfaces. Brand chrome stays navy in both. Test every screen in both modes.
13. PERSISTENCE
Current state | localStorage key refm_v2. JSON-serialized. Per-project versioning. NO Supabase persistence yet.
v1 target | Move REFM project storage to Supabase. New tables: refm_projects, refm_project_versions. Per-user RLS. localStorage becomes cache only. Migration: existing localStorage data uploads to Supabase on next save.
Schema migration policy | Every breaking schema change has a migrator function. Loaded versions auto-upgrade to current schema. Document in CLAUDE-DB.md.
14. FOLDER STRUCTURE
Hubs structure | src/core/ (DB, types, env, formatters), src/shared/ (auth, email, newsletter), src/hubs/main/, src/hubs/training/, src/hubs/modeling/. Modeling Hub: src/hubs/modeling/platforms/refm/ (and reserved bvm/, fpa/, etc.).
REFM internal structure | src/hubs/modeling/platforms/refm/components/ (UI), components/cells/ (cell primitives), components/modules/ (Module N tabs), lib/modules/ (calculation engines per module), lib/exporters/ (excel + pdf builders), lib/agents/ (research + market-rates), lib/state/ (Zustand store after refactor).
ESLint boundary | Enforced. modeling cannot import from training. core/shared shared by all. Already in place.
15. PROCESS RULES (carry over from Phase 1-4)
Ahmad → Claude (chat) → Claude Code | Ahmad describes task. Chat-Claude writes prompt. Ahmad pastes to Claude Code. Code executes, commits, pushes, reports.
Per-phase commit | One logical commit per phase. Type-check + build pass before commit.
Snapshot diff | Mandatory for any change to Module 1 calculation files. scripts/module1-snapshot-diff.ts must exit 0.
No em dashes | Use commas / colons / periods / parentheses / and-or instead. Carries to all written output, code comments, UI strings, exports.
Eyeball verification | After every UI commit, Ahmad verifies in browser before approving next phase. Light + dark both checked.
Stop at boundaries | Each phase pauses for confirmation. No multi-phase scope creep without explicit approval.

## Tracker
REFM Platform: Build Tracker | [7 empty] | Done
Sequenced execution plan. Each phase pauses for verification before next. | [7 empty] | Not Started
In Progress
Ph# | Phase | Deliverable | Status | Start Date | Completion Date | Hours | Dependencies
F0 | Folder restructure | src/hubs/, src/core/, src/shared/, ESLint boundaries, path aliases | Done |  |  |  | Pre-existing
F1 | Design tokens system | src/hubs/modeling/design-tokens/, FAST cells, light+dark, Tailwind wiring, README | Done |  |  |  | Pre-existing
F2 | Excel exporter token retrofit | lib/exporters/excel.ts pure builder, FAST cell colors, fixture script | Done |  |  |  | F1
F3 | PDF exporter token retrofit | lib/exporters/pdf.ts pure builder, FAST cell colors, fixture script | Done |  |  |  | F1
F4 | Module 1 snapshot guard | tests/fixtures/module1-reference.json + scripts/module1-snapshot-diff.ts | Done |  |  |  | F1
F5 | REFM component token retrofit | All 15 REFM files. Phase 4.1-4.15. Hex/rgba grep zero across folder. | Done |  |  |  | F1, F4
F6 | Modeling Hub sidebar shell | /modeling/dashboard sidebar layout, CMS logo, dark mode toggle | Done |  |  |  | F1
F7 | REFM Topbar dark mode toggle | Independent localStorage key, scoped to .app-shell | Done |  |  |  | F5
F8 | Module name editing | ProjectModal edit mode wired, pencil button on Overview + Projects | Done |  |  |  | F5
M1.R | Module 1 typed-shape refactor | Lift hardcoded asset enum to AssetClass[]; replace single-phase model with Phase[]; normalize residentialCosts/hospitalityCosts/retailCosts into a single costs[] keyed by assetId. Calculations bit-identical (snapshot diff exit 0). Persistence migrator handles old refm_v2 shape. | Not started |  |  | 8 | F4 snapshot
M1.5 | Module 1 hierarchy upgrade | Add Master Holding (optional) → Sub-Project → Phase → Asset → Sub-Unit support to Module 1. UI gains Hierarchy tab (5th tab) for managing layers. Existing Timeline/Area/Costs/Financing tabs remain but operate per-Phase. | Not started |  |  | 12 | M1.R
M1.6 | Module 1 Supabase persistence | Migrate from localStorage to Supabase tables refm_projects, refm_project_versions. Per-user RLS. localStorage becomes cache. Migrator uploads existing data on first save. | Not started |  |  | 6 | M1.5
M2.1 | Module 2, Revenue: Sell stream | Per-asset Sell mode: Sub-Units × price grid, indexation, pre-sale velocity schedule, down payment %, payment plan installments, cash collection cohort matrix, revenue recognition profile, sales during operation, receivables roll-forward, sales commission. Outputs to Module1Exports interface for downstream modules. | Not started |  |  | 14 | M1.5
M2.2 | Module 2, Revenue: Operate stream (USAH) | Per-asset Operate mode: Keys × Days × Occupancy = Occupied, ADR + ADR growth, F&B as % of Rooms or per-occupied, Spa, Other. Departmental Revenue + Departmental Expenses + Departmental Income + Undistributed (A&G/Marketing/POM/Utilities) + GOP + Base Mgmt Fee + Adjusted GOP + Fixed (Insurance/FF&E Reserve/Property Tax/Land Lease) + Incentive Mgmt Fee. EBITDA after FF&E Reserve. PAR + POR KPIs. Multi-scenario occupancy curves. | Not started |  |  | 12 | M1.5
M2.3 | Module 2, Revenue: Lease stream | Per-asset Lease mode: Total Lease Area, Loading factor, Vacancy %, Rent/sqm, Rental Growth Rate, OpEx (% of revenue or itemized). NOI = Revenue − OpEx. | Not started |  |  | 6 | M1.5
M2.4 | Module 2, Revenue: Hybrid composition | Hybrid asset combines 2+ streams (e.g., serviced apartments Sell + Operate same units). Streams configured separately, roll up to single asset P&L. Common patterns pre-built: Serviced Apartments, Mixed-Use Building (Lease podium + Operate hotel). | Not started |  |  | 6 | M2.1, M2.2, M2.3
M2.5 | Module 2 UI tabs | Tabs per Asset: Stream config, Pricing/ADR/Rent, Schedules (velocity/occupancy/vacancy), Outputs (per-period revenue + collections). FAST cells throughout. | Not started |  |  | 10 | M2.1-M2.4
M2.6 | Module 2 sample fixture + snapshot guard | Add Module 2 to scripts/snapshot-diff. Cover Sell + Operate + Lease + Hybrid sample assets. Reference numbers verified against MAAD + Hospitality fixture patterns. | Not started |  |  | 4 | M2.5
M3 | Module 3, Operating Expenses | Beyond hospitality direct opex (handled in M2.2): corporate overhead (e.g., New Company Costs SAR 2M/year), Zakat/Tax %, Working Capital days. Per-period schedules. Outputs ready for M5 financial statements. | Not started |  |  | 8 | M2
M4.1 | Module 4, Project IRR / Equity IRR | Unlevered Project IRR (capex out, NOI/EBITDA in, terminal value in). Levered Equity IRR (after debt service). Per Sub-Project. Per Master Holding (when present). | Not started |  |  | 6 | M2, M3
M4.2 | Module 4, FCFE + DDM dual returns | FCFE IRR/MOIC and DDM IRR/MOIC computed in parallel per Sub-Project. Shareholder split when JV (e.g., 65/35) drives per-investor returns. Match Hospitality + Alma model patterns. | Not started |  |  | 6 | M4.1
M4.3 | Module 4, NPV, MOIC, Payback, Margins | NPV at user-discount-rate, MOIC = total distributions / total equity, Payback Year (cumulative cash crosses zero), Development Margin = (Revenue − Cost) / Revenue, Profit on Cost = (Revenue − Cost) / Cost, Cash-on-Cash annual. | Not started |  |  | 4 | M4.1
M4.4 | Module 4, DSCR, ICR, LTC, LTV per period | Coverage and leverage ratios per period. DSCR < 1.2x amber, < 1.0x red. Display in returns dashboard. | Not started |  |  | 4 | M4.1
M4.5 | Module 4, Terminal Value | Terminal Value computed at terminal year per asset: capitalized NOI / cap rate, OR multiple × final-year EBITDA, OR exit price. User picks method per asset. Selling Cost % deducted. | Not started |  |  | 4 | M4.1
M5.1 | Module 5, P&L statement | Per-period P&L per Sub-Project: Revenue (by stream) → COGS (capex amortized over recognized revenue for Sell, none for Operate/Lease) → Gross Profit → OpEx → EBITDA → D&A → EBIT → Interest → EBT → Tax/Zakat → Net Income. | Not started |  |  | 6 | M2, M3, M4
M5.2 | Module 5, Cash Flow statement | Per-period CF per Sub-Project: Operating CF (EBITDA − Tax − ΔWC) + Investing CF (Capex, FF&E Reserve) + Financing CF (Equity drawdown, Debt drawdown, Debt repayment, Interest paid, Dividends) = Net Change. Master Holding consolidated CF when applicable. | Not started |  |  | 6 | M5.1
M5.3 | Module 5, Balance Sheet | Per-period BS: Land + WIP + Receivables + Cash = Loan + Payables + Equity + Retained Earnings. Reconciles to CF. | Not started |  |  | 6 | M5.2
M5.4 | Module 5, Cash Sweep waterfall | Available cash − Min cash required = Distributable to dividend. Per scenario. Master Holding consolidation when applicable. | Not started |  |  | 4 | M5.2
M6 | Module 6, Reports & Visualizations | Tabular and chart views of Module 4 + Module 5 outputs. Charts: Cashflow waterfall, Sources & Uses, Returns by year, Capital stack. Per-period drill-down. Print-ready layouts. | Not started |  |  | 8 | M5
M7.1 | Module 7, Scenario engine | Scenario delta storage. 3 primary (Base/Management/Upside) + unlimited custom. Each scenario stores deltas for: occupancy curves, ADR growth, sale velocity, DP%, escalation, payment plan, rental growth, vacancy. Active scenario toggle drives display. | Not started |  |  | 8 | M2
M7.2 | Module 7, Sensitivity tables | 2D sensitivity: NPV vs discount rate, IRR vs occupancy, IRR vs sale price, IRR vs ADR. Conditional formatting. Tornado charts. | Not started |  |  | 6 | M7.1, M4
M7.3 | Module 7, Breakeven analysis | Per asset: solve for occupancy that hits EBITDA / Interest / Debt Service breakeven. For Sell assets: solve for sale price that breaks even on equity invested. Match Hospitality model breakeven format. | Not started |  |  | 6 | M4
M8.1 | Module 8, Portfolio rollup | Master Holding rollup view across all Sub-Projects: consolidated revenue, EBITDA, capex, debt, returns. Per-Sub-Project comparison table. Tracks Hospitality 7-project model + Alma 7-fund model patterns. | Not started |  |  | 8 | M5
M8.2 | Module 8, Cross-project allocation | Project-scope cost allocation across Sub-Projects (master infrastructure, master marketing, master overhead) by share rules (revenue share, capex share, gfa share). | Not started |  |  | 4 | M8.1
M9.1 | Module 9, Research agent | Anthropic SDK + web search. City market intel: population, demographics, GDP, sectors, infra, regs. 7-day cache per city. | Not started |  |  | 8 | M2
M9.2 | Module 9, Market Rates agent | Anthropic SDK + web search. ADR/RevPAR/Cap Rates/Rental rates/Construction costs by (city, asset_type). 7-day cache per pair. | Not started |  |  | 8 | M9.1
M9.3 | Module 9, Agent UI integration | Per asset/parcel, 'Suggest from market' button calls relevant agent, displays result with override input. User-set values priority. Audit log of suggested vs accepted values. | Not started |  |  | 6 | M9.2
M10 | Module 10, Collaborate (Pro tier) | Multi-user project access, role-based permissions (already has RBAC modal), comment threads, change history, share link. Defer post-launch if scope tight. | Optional v1.5 |  |  | 16 | M1.6 Supabase
M11.1 | Module 11, Final Dashboard layout | Project home screen replacing current Overview. Top scenario switcher. KPI grid (IRR FCFE, IRR DDM, MOIC, NPV, Payback, Dev Margin, PoC, CoC, DSCR avg, LTC, LTV, Equity Multiple). | Not started |  |  | 6 | M4, M5, M7
M11.2 | Module 11, Charts package | Cashflow waterfall, Sources & Uses bar, Returns by year line, Sensitivity tornado, Breakeven occupancy chart, Capital stack pie, Distribution timeline. Recharts. | Not started |  |  | 8 | M11.1
M11.3 | Module 11, Live scenario switcher | Toggle scenarios, all KPIs and charts refresh without reload. Custom scenario picker for non-primary scenarios. | Not started |  |  | 4 | M11.1, M7.1
M12.1 | Module 12, IM PDF builder | Sections: Cover, Exec Summary, Highlights, Market, Location, Project Description, Development Program, Financial Summary, Investment Structure, Comparables, Risks, Macro, Developer Profile. @react-pdf/renderer. Token-driven. | Not started |  |  | 12 | M11
M12.2 | Module 12, IM PPT builder | Same content, PPT format. pptxgenjs library. Token-driven. | Not started |  |  | 8 | M12.1
M13.1 | Module 13, Excel formula export (Enterprise) | Full formula-driven workbook: named ranges, XIRR/XNPV, scenario switch via INDIRECT, 2D sensitivity tables, all Module 5 statements. Replicates entire model in Excel. | Not started |  |  | 16 | M5, M7
M13.2 | Module 13, PDF Whitelabel (Enterprise) | Per-client branded PDF: logo, color override, custom footer/header. Reads from client_branding table. | Not started |  |  | 6 | F3
Q1 | Integration QA, Hospitality fixture | Build the 7-project hospitality model from earlier (Project 1-7, hotel + retail + office) end-to-end through the platform. Reconcile outputs against the Excel reference. | Not started |  |  | 10 | M1-M11
Q2 | Integration QA, MAAD fixture | Build the 5-asset 3-phase MAAD residential + hotel model end-to-end. Reconcile against Excel. | Not started |  |  | 10 | M1-M11
Q3 | Integration QA, Alma fixture | Build a 7-fund Master Holding + sub-funds + zones model (subset of full Alma, Master Fund + 2-3 sub-funds is enough to validate hierarchy). Reconcile. | Not started |  |  | 12 | M1-M11
Q4 | End-to-end snapshot guards | Add fixtures + snapshot diffs for M2-M11 covering all calculation paths. Mandatory exit 0 before any future commit touching modules. | Not started |  |  | 6 | Q1-Q3
L1 | Pre-launch hardening | Performance audit, accessibility pass, error boundaries, loading states, empty states, mobile-responsive checks for view-only. | Not started |  |  | 8 | Q4
L2 | Pricing tier integration | Re-introduce subscription system removed in Phase 5 admin cleanup. Plan-based feature gating restored. Stripe / payment integration. | Not started |  |  | 12 | L1
L3 | Launch | Public REFM availability for app.financialmodelerpro.com modeling hub. Module 10 (Collaborate) post-launch v1.5. | Not started |  |  | 4 | L2
| TOTAL |  |  |  |  | 332

## Prompts
REFM Platform: Paste-Ready Prompts
Each prompt is one execution unit for Claude Code. Read the Architecture sheet first. Comply with all 15 sections. Snapshot diff exit 0 mandatory for any change touching Module 1 calculations.
Ph# | Phase | Prompt | Status | Start Date | Completion Date
M1.R | Module 1 typed-shape refactor | Refactor Module 1 to support multi-asset and multi-phase data shape without changing calculation outputs. Read Architecture sheet sections 1, 2, 8, 14 before starting. Target outcome: 1. Replace the hardcoded `'residential' ¦ 'hospitality' ¦ 'retail'` string union with a typed AssetClass[] array. Each asset has: id, name, type (from 20 pre-built or custom string), category ('Sell' ¦ 'Operate' ¦ 'Lease' ¦ 'Hybrid'), allocationPct (% of project GFA), deductPct, efficiencyPct. 2. Replace the single Construction-Operations timeline with a Phase[] array. Each phase has: id, name, constructionStart, constructionPeriods, operationsStart, operationsPeriods, overlapPeriods. Single-phase users have one phase. Multi-phase users add more. 3. Normalize the parallel `residentialCosts[] / hospitalityCosts[] / retailCosts[]` arrays into a single `costs[]` keyed by `assetId` (and optional `phaseId` for phase-specific costs). 4. Lift state from 30+ useState hooks in RealEstatePlatform.tsx into a Zustand store at `src/hubs/modeling/platforms/refm/lib/state/module1-store.ts`. Store exposes typed selectors and actions. Component reads via selectors. 5. Persistence migrator: on load, detect old refm_v2 shape (3 hardcoded asset arrays) and convert to new shape (1 normalized assets[] + 1 normalized costs[] + 1 phases[] with single phase). Preserve all data. 6. Calculations bit-identical. Snapshot diff `npx tsx scripts/module1-snapshot-diff.ts` must exit 0 against existing baseline. Constraints: - Do not introduce new calculations. Only restructure data and adapt existing calc functions to read from new shape. - buildAssetFinancing, calculateItemTotal, distributeCost, getAreas, allocateToAssets, calcItemTotalV14, getAssetDirectCost all preserve their signatures externally; internally they iterate the new assets[] array. - Same-for-all mode preserved as a UI/state preference, propagating non-land cost lines across all assets in costs[]. - All 4 Module 1 tabs (Timeline / Area / Costs / Financing) continue rendering correctly, in light + dark. - FAST cell convention preserved. Verification: - Snapshot diff exit 0 - Type-check + build pass - Manually: load existing project, verify all numbers identical - Eyeball Module 1 in light + dark One commit. Push to main. | Not started | 0 | 0
M1.5 | Module 1 hierarchy upgrade | Add the 5-layer hierarchy to Module 1. Read Architecture sheet section 1 before starting. Target outcome: 1. New types: MasterHolding (optional), SubProject, Phase, Asset, SubUnit. SubProject has: id, name, currency, masterHoldingId (nullable), revenueShareToMaster (% if linked to master). 2. New "Hierarchy" tab in Module 1 (5th tab, becomes default landing of Module 1). UI: tree view of MasterHolding (optional) → SubProjects → Phases → Assets → SubUnits with create/edit/reorder controls. 3. Existing tabs (Timeline / Area / Costs / Financing) operate within a selected Phase context. Phase selector at top of these tabs. 4. SubUnit: per-asset inventory with name, count or area, price/rate (auto-driven by asset category Sell/Operate/Lease). 5. Master Holding: optional. When present, has its own land cost, debt, revenue share % from sub-projects, P&L, returns. UI shows separate "Master Holding" entity in Hierarchy tab. 6. Persistence: extend Zustand store and Supabase schema (preview only, actual Supabase migration in M1.6). Migrator handles old single-project shape. Constraints: - Single-project users (no Master Holding, one Sub-Project, one Phase) get a streamlined UX. Master Holding panel hidden until enabled. Multi-phase users see Phase selector. Default new project: 1 Sub-Project + 1 Phase + empty assets array. - Snapshot diff still passes for the single-phase fixture. - FAST cells throughout new Hierarchy tab. Verification: - Snapshot diff exit 0 (single-phase legacy fixture) - New fixture for multi-phase + multi-asset case added to tests/fixtures/ - Type-check + build pass - Eyeball: create a 3-phase project, add assets to each phase, switch phases, verify isolation | Not started
M1.6 | Module 1 Supabase persistence | Migrate REFM project storage from localStorage to Supabase. Read Architecture sheet sections 13, 14 before starting. Target outcome: 1. Two tables: refm_projects (id, user_id, name, location, currency, created_at, updated_at, status, master_holding JSONB, sub_projects JSONB) and refm_project_versions (id, project_id, version_name, snapshot JSONB, created_at). 2. Migration file: db/migrations/NNN_refm_projects.sql with both tables + RLS policies (per-user read/write). 3. Server actions or API routes for: list projects, get project, save project, save version, load version, delete project. Use Supabase service role for server, client uses anon + RLS. 4. Module 1 store reads/writes via these actions. localStorage becomes a cache for offline editing. On save: write to Supabase, update localStorage. On load: read from Supabase, fallback to localStorage if offline. 5. Migrator: on first load of existing user, detect localStorage refm_v2 data and upload to Supabase. After successful upload, retain localStorage as cache. Constraints: - Snapshot diff still passes - No breaking change for existing users; migrator handles transition transparently - Type-safe: generate Supabase types and use them in store Verification: - Snapshot diff exit 0 - Type-check + build pass - Test with two users: each can only see own projects (RLS verified) - Refresh browser: data persists from Supabase | Not started
M2.1 | Module 2 Revenue, Sell stream | Build the Sell revenue stream for Module 2. Read Architecture sheet sections 7, 1, 12 before starting. Reference existing MAAD residential model (already discussed), use its Sell pattern. Target outcome: 1. New file `lib/modules/module2-revenue.ts` (replace existing 2-line stub). 2. Per-asset Sell config: SubUnits[] each with count/area, price/rate, indexation factor. Pre-sale velocity schedule (% sold per year, sums ≤100%, residual = post-handover). Down Payment % per year. Payment plan: installment count after DP. Cash collection cohort matrix (Year-N sales generate collections in Year N, N+1...). Revenue Recognition profile (separate from cash, recognizes over construction period). 3. Sales Commission %: deducted from revenue, ties back into Module 1 capex via percent_base loop. 4. Receivables Roll-Forward per period: Opening + New Sales − Collected = Closing. 5. Sales During Operation: residual unsold inventory sold post-handover at indexed price. 6. Outputs: per-asset per-period revenue (recognized), cash collected, receivables balance, units sold cumulative. 7. UI: new Module 2 tab "Revenue" with sub-tab per Asset. FAST cells throughout. Sub-Unit grid editable. Schedule grids (velocity/DP/payment plan) editable. Outputs table read-only. 8. Wires into Module 1 Exports interface, produce module2 outputs object that downstream modules (M4, M5, M11) will consume. Constraints: - Reference: MAAD model 5 sellable assets pattern (Branded Apartments T2/T3, T4/T5, Residential Tower 01, etc.) - Indexation compounds annually - Match the pattern exactly: pre-sale year × payment plan installments produces 2D cohort matrix - No hardcoded colors, FAST cells only Verification: - New snapshot fixture tests/fixtures/module2-sell-reference.json with sample 1BR/2BR Branded Apartments asset - Snapshot diff for Module 2 outputs exit 0 - Type-check + build pass - Eyeball: configure sample asset, verify revenue/collection numbers tie out manually | Not started
M2.2 | Module 2 Revenue, Operate stream (USAH) | Build the Operate revenue stream for Module 2 with full Uniform System of Accounts for Hotels. Read Architecture sheet sections 6, 7 before starting. Reference Hospitality model (7-project) Hotel P&L + Alma H sheets. Target outcome: 1. Per-asset Operate config: Keys (or Units) by Sub-Unit type (Twin/King/Suite), Days/Year (default 365), Occupancy % per period (multi-scenario), ADR per Sub-Unit, ADR Growth Rate per year (compounding). 2. Revenue: Departmental, Rooms (Occupied × ADR), F&B (% of Rooms or Occupied × Guests/Room × Spend/Guest, user picks method), Spa/Health Club (% of Rooms), Other (% of Rooms). 3. Departmental Expenses: % of departmental revenue. Defaults Rooms 20%, F&B 55%, Spa 50%, Other 40%. User configurable. 4. Departmental Income: Departmental Revenue − Departmental Expenses. 5. Undistributed Operating Expenses: A&G, Group Services, Marketing/Sales, POM, Utilities. Each as % of total revenue. Defaults A&G 8%, Marketing 5%, POM 4%, Utilities 4%, Group Services 3%. 6. Gross Operating Profit (GOP): Departmental Income − Undistributed. 7. Base Management Fee: % of total revenue. Default 2%. 8. Adjusted GOP: GOP − Base Mgmt Fee. 9. Fixed Expenses: Insurance % of revenue, Replacement Reserve / FF&E Reserve % of revenue, Property Tax (lump or %), Land Lease (separate toggle). 10. Incentive Management Fee: % of Adjusted GOP. Default 0%, user configurable. 11. EBITDA after FF&E Reserve: final operating output. 12. KPIs: PAR (Per Available Room) = Revenue / (Keys × Days), POR (Per Occupied Room) = Revenue / Occupied. 13. UI: per-asset config form with all defaults pre-filled. FAST cells. Output table per period showing full P&L breakdown. Constraints: - Match USAH structure exactly. Reference the Hospitality fixture model H 1-MA Hospitality sheet. - Multi-scenario occupancy: when active scenario changes, occupancy curve switches. - Operations Start Year is per asset, not project-level. - All hardcoded numbers above are defaults; user overrides per asset. Verification: - New snapshot fixture tests/fixtures/module2-operate-reference.json (sample 200-key 4-star hotel) - Numbers tie to manual calculation against Hospitality fixture pattern - Snapshot diff exit 0 - Type-check + build pass - Eyeball PAR + POR display correctly | Not started
M2.3 | Module 2 Revenue, Lease stream | Build the Lease revenue stream for Module 2. Read Architecture sheet section 7. Reference MAAD Support Retail + Hospitality model retail pattern. Target outcome: 1. Per-asset Lease config: Total Lease Area sqm, Loading Factor % (gross-to-rentable conversion), Vacancy % per period (multi-scenario), Base Rent SAR/sqm/year, Rental Growth Rate % per year (compounding). 2. Revenue per period: Rentable = Gross × (1 − Loading%). Leased = Rentable × (1 − Vacancy%). Revenue = Leased × Rent × (1 + Growth)^year. 3. OpEx: % of revenue (default 15%) OR itemized: Property Mgmt %, Asset Mgmt %, Utilities %, Insurance %, Reserve %. User picks method. 4. NOI per period = Revenue − OpEx. 5. UI: per-asset config form. FAST cells. Output table per period showing Rentable / Leased / Revenue / OpEx / NOI. Constraints: - Match MAAD pattern (Support Retail Phase 2 + Phase 3, Operations Start Year per asset). - Operations Start Year per asset, not project-level. - Indexation compounds annually. Verification: - New snapshot fixture tests/fixtures/module2-lease-reference.json (sample retail asset) - Snapshot diff exit 0 - Type-check + build pass | Not started
M2.4 | Module 2 Revenue, Hybrid composition | Build Hybrid revenue mode that composes 2+ streams within one asset. Read Architecture sheet section 7. Target outcome: 1. Hybrid asset has streams[] array. Each stream is a {category: 'Sell' ¦ 'Operate' ¦ 'Lease', config: SellConfig ¦ OperateConfig ¦ LeaseConfig}. Streams run in parallel. 2. Pre-built hybrid patterns user can insert: Serviced Apartments (Sell stream for post-handover sales + Operate stream for pre-handover service), Mixed-Use Building (Lease stream for podium retail + Operate stream for hotel floors above). 3. Per-asset rollup: sum revenue across streams. Display per-stream breakdown for transparency. 4. UI: when asset category = 'Hybrid', show multi-stream config interface. User can add/remove/reorder streams. Each stream uses the same form as standalone Sell/Operate/Lease. Constraints: - A Hybrid asset can have any combination of stream categories - Stream-level outputs preserved separately for downstream attribution Verification: - New snapshot fixture for hybrid asset (Serviced Apartments mirroring MAAD Residential Tower 01) - Snapshot diff exit 0 | Not started
M2.5 | Module 2 UI tabs | Build the full Module 2 UI shell. Target outcome: 1. Module 2 main tab contains: per-asset list (left), per-asset detail (right). Detail has sub-tabs per asset based on category. 2. Sub-tabs for any asset: Stream Config, Pricing/ADR/Rent, Schedules (velocity/occupancy/vacancy curves), Outputs (per-period revenue, collections, receivables). 3. All inputs use InputCell. All calculated outputs use FormulaCell. SectionHeader for major divisions. 4. Both light + dark mode. 5. Asset list shows asset name + category badge + revenue stream count. Verification: - Type-check + build pass - Eyeball every sub-tab in light + dark - Sample fixture loads and renders all categories | Not started
M2.6 | Module 2 snapshot guard | Add Module 2 to the snapshot diff system. Target outcome: 1. Extend scripts/module1-snapshot.ts to scripts/modeling-snapshot.ts (renamed) covering Module 1 + Module 2. 2. New baseline file tests/snapshots/modeling-baseline.json containing Module 1 + Module 2 outputs for the multi-asset multi-phase fixture. 3. Diff script returns exit 0 only if both Modules match baseline. 4. Update Phase 4 prep documentation in scripts/module1-pipeline.ts header comment to reflect new contract. Verification: - Run diff: exit 0 - Modify a calculation intentionally: diff exit 1 with clear failure message - Revert: exit 0 | Not started
M3 | Module 3, Operating Expenses | Build Module 3 (corporate-level OpEx separate from per-asset operating costs). Read Architecture sheet sections 5, 6. Target outcome: 1. New file lib/modules/module3-opex.ts (replace stub). 2. Per Sub-Project corporate overhead: New Company Costs (lump sum SAR/year, default 2M, growing), Working Capital days (DSO, DPO, DIO), Tax/Zakat % rate. 3. Per-period schedule: corporate overhead × inflation, WC change calculation, Zakat applied to net income (computed in M5). 4. UI: Module 3 tab with corporate cost grid (FAST inputs), schedules (FormulaCells), and a small KPI panel. 5. Outputs feed Module 5 financial statements. Verification: - Snapshot guard extended - Type-check + build pass | Not started
M4.1 | Module 4, Project IRR / Equity IRR | Build the core IRR engine for Module 4. Read Architecture sheet sections 4, 5. Target outcome: 1. New file lib/modules/module4-returns.ts (replace stub). 2. Project IRR (unlevered): assemble per-period unlevered cash flows. Year 0 = (capex). Year 1+ = NOI/EBITDA + WC change. Terminal year = + Terminal Value − Selling Cost. Run XIRR against the cashflow series + dates. 3. Equity IRR (levered): assemble per-period equity cash flows. Year 0 = (equity drawdowns). Year N = + dividends − additional equity injection. Terminal year = + equity terminal value. XIRR. 4. Per Sub-Project. Per Master Holding (when present, treats SubProjects' revenue share + Master debt as flows). Constraints: - Use a robust XIRR implementation (no native JS function; build or import a tested one) - Handle no-cashflow scenarios gracefully (display "n/a") - All numbers feed Module 11 dashboard Verification: - Snapshot fixture for IRR validated against Excel XIRR for same fixture - Tolerance: 0.01% deviation max - Type-check + build pass | Not started
M4.2 | Module 4, FCFE + DDM dual returns | Add FCFE + DDM dual computation per Sub-Project. Read Architecture sheet section 4. Reference Alma Master Fund + sub-fund pattern. Target outcome: 1. FCFE IRR: Free Cash Flow to Equity per period (Net Income + D&A − Capex − ΔWC + ΔDebt). Plus Terminal Value at terminal year. XIRR. 2. DDM IRR: Dividend Discount Model (Distributable Cash to Equity Holders only, after Min Cash Required). Plus Terminal Value. XIRR. 3. MOIC for each: Total Distributions / Total Equity. 4. JV split: when Sub-Project has joint venture shareholding (e.g., 65% / 35%), compute per-investor IRR and MOIC. UI shows split returns. Verification: - Snapshot fixture matches Alma model FCFE / DDM IRRs to 0.5% tolerance - JV split case validated against Hospitality model 7-project DI + Proper IRR pattern | Not started
M4.3 | Module 4, NPV, MOIC, Payback, Margins | Add the auxiliary return metrics. Target outcome: 1. NPV: user-set discount rate (default 10%), XNPV against unlevered cashflows. 2. MOIC: total distributions / total equity invested, both Sub-Project level and per-investor when JV. 3. Payback Year: first period where cumulative cash flow turns positive. 4. Development Margin %: (Total Revenue − Total Cost) / Total Revenue. 5. Profit on Cost %: (Total Revenue − Total Cost) / Total Cost. 6. Cash-on-Cash: per-year NOI / Equity Invested. Verification: - Manual reconciliation against MAAD + Alma fixtures - Snapshot guard extended | Not started
M4.4 | Module 4, DSCR, ICR, LTC, LTV | Add coverage and leverage ratios per period. Target outcome: 1. DSCR per period: NOI / (Interest + Principal Repayment). Average DSCR + min DSCR reported. 2. ICR per period: NOI / Interest. Average + min reported. 3. LTC: Total Debt / Total Capex. 4. LTV: Total Debt / Asset Value (use total revenue × cap rate or similar approximation). 5. Display in Module 4 ratios panel and Module 11 dashboard. < 1.2x DSCR amber, < 1.0x red. Verification: - Snapshot fixture extended - Color-coding tested in UI | Not started
M4.5 | Module 4, Terminal Value | Build Terminal Value computation per asset. Read Architecture sheet section 4. Target outcome: 1. Per asset, user picks one of three methods: a) Capitalized NOI: NOI(terminal year) / Cap Rate b) Multiple × EBITDA: User-set multiple × final-year EBITDA c) Exit Sale Price: Direct user-input 2. Selling Cost % deducted from terminal value (default 2%). 3. Terminal Value summed across assets per Sub-Project, added as final-year inflow in Module 4 IRR. Verification: - Match Hospitality model "Exit Value" pattern - Match MAAD model exit calculation | Not started
M5.1 | Module 5, P&L Statement | Build the per-period P&L per Sub-Project and Master Holding. Read Architecture sheet section 6. Target outcome: 1. New file lib/modules/module5-statements.ts (replace stub). 2. P&L Structure per Sub-Project per period: Revenue (by stream Sell/Operate/Lease, summed) → COGS (capex amortized over recognized revenue for Sell, none for Operate/Lease) → Gross Profit → OpEx (per asset operating costs from M2.2 + M2.3 + M3 corporate) → EBITDA → D&A (capex / useful life) → EBIT → Interest (from M1 Financing) → EBT → Tax/Zakat → Net Income. 3. Master Holding P&L: Revenue Share from Sub-Projects + Interest Income on intra-group loans − Master overhead − Interest on Master debt − Tax = Net Income. 4. UI: Module 5 sub-tab "P&L" with year columns, line items as rows. FAST cells (calculations black on grey). 5. Both light + dark. Verification: - Match MAAD CF Phase 1, 2 & 3 P&L structure - Snapshot guard extended | Not started
M5.2 | Module 5, Cash Flow Statement | Build the per-period Cash Flow Statement. Target outcome: 1. CF per Sub-Project: Operating CF (EBITDA − Tax − ΔWC) + Investing CF (Capex, FF&E Reserve) + Financing CF (Equity drawdown, Debt drawdown, Debt repayment, Interest paid, Dividends) = Net Change in Cash. Opening + Net Change = Closing. 2. Master Holding consolidated CF when applicable. 3. UI: Module 5 sub-tab "Cash Flow" with year columns. Verification: - Tie out to P&L (Net Income + non-cash adjustments → operating CF) - Closing cash matches BS in M5.3 | Not started
M5.3 | Module 5, Balance Sheet | Build the per-period Balance Sheet. Target outcome: 1. Assets: Land + WIP (capex incurred not yet operating) + Receivables + Cash. Liabilities: Loan Balance + Payables. Equity: Equity Contributed + Retained Earnings. 2. Reconcile Assets = Liabilities + Equity per period. 3. UI: Module 5 sub-tab "Balance Sheet". Verification: - BS balances per period (within 0.01 SAR rounding tolerance) - Reconciles to CF statement | Not started
M5.4 | Module 5, Cash Sweep Waterfall | Build the Cash Sweep distribution mechanics. Target outcome: 1. Per period: Available Cash − Min Cash Required = Distributable. Distributable goes to equity per JV split (or 100% to equity if single investor). 2. Master Holding sweep: Sub-Project distributions roll up to Master Holding, sweep continues at Master level if applicable. 3. UI: visual waterfall diagram per period. Verification: - Match Hospitality model Cash Sweep waterfall pattern | Not started
M6 | Module 6, Reports & Visualizations | Build the Module 6 tabular and chart reports. Target outcome: 1. New file lib/modules/module6-reports.ts (replace stub). 2. Report views: Annual Summary, Quarterly Detail (if monthly model), 5-year forecast, Cumulative metrics. 3. Charts (Recharts, FAST-compliant colors): Cashflow Waterfall, Sources & Uses bar, Returns by Year line, Capital Stack pie. 4. Print-ready layout with consistent margins. 5. UI: Module 6 tab with chart selector + table view. Verification: - Charts render in light + dark - Numbers reconcile to M5 statements | Not started
M7.1 | Module 7, Scenario engine | Build the scenario delta storage and switching. Read Architecture sheet section 4. Target outcome: 1. New file lib/modules/module7-scenarios.ts (replace stub). 2. Scenario: { id, name, isPrimary, deltas: { occupancyCurve?, adrGrowth?, saleVelocity?, downPayment?, escalation?, paymentPlan?, rentalGrowth?, vacancy? } }. 3. Three primary scenarios pre-seeded: Base, Management, Upside. User can edit primaries' deltas. User can add custom scenarios (unlimited). 4. Active scenario state in Zustand store. Toggle in Topbar + in Module 11 dashboard. 5. Calculations re-run when active scenario changes. Module 2 (revenue) reads scenario deltas to override base assumptions where set. Verification: - Switch scenarios, verify revenue + IRR change accordingly - Snapshot fixture for each primary scenario | Not started
M7.2 | Module 7, Sensitivity tables | Add 2D sensitivity tables and tornado charts. Target outcome: 1. 2D tables: NPV vs Discount Rate (rows) × Occupancy (cols). IRR vs Sale Price × Occupancy. IRR vs ADR × Occupancy. User can configure axes. 2. Conditional formatting: gradient from red (low) to green (high). 3. Tornado chart: each variable's impact on a target metric (e.g., IRR), bars show min/max range. Verification: - Numbers reconcile (corner values match base case) - Charts render correctly | Not started
M7.3 | Module 7, Breakeven analysis | Build per-asset breakeven solver. Target outcome: 1. Per Operate asset: solve for occupancy that hits EBITDA / Interest / Debt Service breakeven (3 thresholds). 2. Per Sell asset: solve for sale price that breaks even on equity invested (NPV = 0 at user-discount-rate). 3. Per Lease asset: solve for vacancy or rent that hits breakeven. 4. UI: breakeven table per Sub-Project with all assets, side-by-side breakeven values. Verification: - Match Hospitality model breakeven analysis pattern (3 cases per project) | Not started
M8.1 | Module 8, Portfolio rollup | Build the Master Holding portfolio view. Read Architecture sheet sections 1, 11. Target outcome: 1. New file lib/modules/module8-portfolio.ts (replace stub). 2. Rollup: across all Sub-Projects belonging to a Master Holding, sum revenue, EBITDA, capex, debt, equity, distributions per period. 3. Per-Sub-Project comparison table: name, status, IRR, MOIC, capex, terminal value, returns. 4. Top-level KPIs at portfolio level. 5. UI: Module 8 tab with rollup summary + comparison table + per-Sub-Project drill-down. Verification: - Match Hospitality 7-project Return Analysis consolidated rollup - Match Alma Consolidated Summary pattern | Not started
M8.2 | Module 8, Cross-project allocation | Add project-scope cost allocation across Sub-Projects. Target outcome: 1. Allocation rules at Master Holding level: master infrastructure cost, master marketing cost, master overhead. User picks share basis: revenue share / capex share / GFA share. 2. Allocations flow into Sub-Project cost stacks as project-scope items. Verification: - Numbers reconcile (sum of Sub-Project allocations = Master cost) | Not started
M9.1 | Module 9, Research agent | Build the city market research AI agent. Read Architecture sheet section 9. Target outcome: 1. New file lib/agents/research-agent.ts (replace stub at app/api/agents/research/route.ts). 2. POST endpoint accepts {city, country?}. Calls Anthropic SDK with web search tool. Prompt asks for: population, demographics breakdown, GDP, key sectors, transport infrastructure, regulatory environment for real estate, recent market trends. 3. Response cached in Supabase table agent_research_cache (key: city normalized lowercase, ttl 7 days). 4. Returns structured JSON: { population, demographics, gdp, sectors, infrastructure, regulations, marketTrends, sources[] }. 5. Cost guard: max 1 call per (city, day) per user. Verification: - Test with "Riyadh", returns reasonable Saudi market intel - Cache hit on second call within 7 days | Not started
M9.2 | Module 9, Market Rates agent | Build the market rates AI agent. Target outcome: 1. New file lib/agents/market-rates-agent.ts. 2. POST endpoint accepts {city, assetType}. Calls Anthropic SDK with web search. Asks for: ADR (if hospitality), RevPAR, Cap Rate, Rental rates per sqm (if lease), Construction cost per sqm, Land rates per sqm, recent comparable transactions. 3. Cached per (city, assetType) for 7 days. 4. Returns structured JSON with ranges (low/avg/high) plus sources[]. Verification: - Test with (Riyadh, Hotel 5-star), returns reasonable Saudi luxury hotel ADR ~SAR 1500-2500 - Cache hit confirmed | Not started
M9.3 | Module 9, Agent UI integration | Add the "Suggest from market" UI affordance throughout REFM. Target outcome: 1. Per land parcel: "Suggest land rate" button calls market-rates agent. 2. Per Operate asset: "Suggest ADR / Cap Rate / Construction cost" button. 3. Per Lease asset: "Suggest rental rate" button. 4. UI: agent suggestion appears as advisory text near input. User-set value takes priority. Audit log stored: timestamp, suggested value, accepted/overridden, final value. 5. "Last refreshed N days ago" displayed with manual refresh button. Verification: - Click suggest button, see suggestion populate, override it, save, verify override persists not suggestion | Not started
M11.1 | Module 11, Final Dashboard layout | Build the Final Dashboard as the project home screen. Read Architecture sheet section 11. Target outcome: 1. New file lib/modules/module11-dashboard.ts and corresponding components. 2. Top: Scenario Switcher (toggle Base/Management/Upside or pick Custom). 3. KPI Grid (12 tiles): IRR FCFE, IRR DDM, MOIC, NPV, Payback Year, Development Margin %, Profit on Cost %, Cash-on-Cash avg, DSCR avg, LTC, LTV, Equity Multiple. 4. Each tile uses KpiCard primitive. 5. Becomes the default view after Module 1 setup is complete (replaces current Overview). 6. Both light + dark. Verification: - All KPIs display with correct units and formatting - Eyeball in light + dark | Optional v1.5
M11.2 | Module 11, Charts package | Add the chart suite to Module 11. Target outcome: 1. Cashflow Waterfall chart: capex outflows, revenue inflows, debt service, equity returns over time. Recharts. 2. Sources & Uses bar chart: equity, debt, revenue (sources) vs land, hard cost, soft cost, financing (uses). 3. Returns by Year line chart: cumulative IRR or annual returns. 4. Sensitivity Tornado chart: top 5 variables by impact on IRR. 5. Breakeven Occupancy chart: gauge or threshold meter. 6. Capital Stack pie: equity vs debt vs land in-kind. 7. Distribution Timeline: dividends per year stacked. 8. All charts use FAST-compliant token colors. Light + dark. Verification: - All charts render - Colors token-driven (no hex) | Not started
M11.3 | Module 11, Live scenario switcher | Wire the scenario switcher to live-refresh the dashboard. Target outcome: 1. Toggle scenarios in dashboard top bar. All KPIs and charts refresh without page reload. 2. Custom scenarios accessible via dropdown menu. 3. State managed via Zustand active scenario selector. Verification: - Switch scenarios rapidly, see all numbers + charts update smoothly - No flash of stale data | Not started
M12.1 | Module 12, IM PDF builder | Build the Investment Memorandum PDF. Read Architecture sheet section 10. Target outcome: 1. New file lib/exporters/im-pdf.ts using @react-pdf/renderer. 2. Sections (each its own component): Cover, Executive Summary, Project Highlights, Market Overview, Location, Project Description, Development Program, Financial Summary, Investment Structure, Comparables, Risks & Mitigations, Macro Outlook, Developer Profile. 3. Sections pull data from Modules 1-11. 4. Token-driven (FAST colors + chrome navy). 5. Output: 25-50 page PDF. Verification: - Generate IM for sample project - All sections populated | Not started
M12.2 | Module 12, IM PPT builder | Add PPT export of IM same content. Target outcome: 1. New file lib/exporters/im-pptx.ts using pptxgenjs library. 2. Same content as PDF but slide-formatted. 3. ~20-30 slides. Verification: - Open in PowerPoint, verify rendering | Not started
M13.1 | Module 13, Excel formula export (Enterprise) | Build the Enterprise-tier formula-driven Excel export. Target outcome: 1. New file lib/exporters/excel-formula.ts using exceljs. 2. Full formula model: named ranges (e.g., NamedRange "TaxRate" → cell), XIRR/XNPV functions, scenario switch via INDIRECT(scenario_name & "!" & cell), 2D sensitivity tables with TABLE function or manual grid, all Module 5 statements with cross-sheet references (green-text FAST convention). 3. Replicates the entire calc chain in Excel. 4. Token-driven cell formatting. Verification: - Open generated file in Excel, verify all formulas calculate - Modify input cell, see derived cells recalculate - All FAST conventions visible | Not started
M13.2 | Module 13, PDF Whitelabel (Enterprise) | Add per-client branded PDF export. Target outcome: 1. New file lib/exporters/pdf-whitelabel.ts. 2. Reads client_branding table (logo, primary color, footer text, font preference). 3. Wraps existing PDF basic with custom branding. Verification: - Two clients with different branding produce visually distinct PDFs | Not started
Q1 | Integration QA, Hospitality fixture | Run the 7-project Hospitality model end-to-end through the platform. Target outcome: 1. Recreate the 7-project hospitality model (Project 1-7) in REFM: - Master Holding: optional, but in this case 7 sub-projects with shared P&L view - 7 Sub-Projects, each with hotel + retail (+ office for P1) - Phased construction starts across years - Use exact inputs from the reference Excel 2. Reconcile output against reference Excel: - Per-Sub-Project Total Capex within 0.5% - Per-Sub-Project IRR within 0.5% - Consolidated DDM IRR within 0.5% 3. Document any discrepancies found and fix. Verification: - All 7 projects modeled - Reconciliation report saved to tests/qa/hospitality-reconciliation.md | Not started
Q2 | Integration QA, MAAD fixture | Run the MAAD residential 5-asset 3-phase model end-to-end. Target outcome: 1. Recreate MAAD model: - 1 Sub-Project, 3 Phases (Phase 1 VOCO Hotel operating 2026, Phase 2 multiple assets ops 2029, Phase 3) - 5 Assets: Branded Apartments T2&T3, T4&T5, Residential Tower 01, Hotel 01, Support Retail - Hybrid for Residential Tower 01 (Sell + Operate) 2. Reconcile against MAAD Excel: - Total capex SAR 5,604,977k within 0.5% - 2026 Net Cash Flow within 0.5% - Closing cash through 2030 within 1% Verification: - Model loads - Reconciliation report saved | Not started
Q3 | Integration QA, Alma fixture | Run a Master Holding + Sub-Funds Alma model subset end-to-end. Target outcome: 1. Recreate Alma subset: - 1 Master Holding (carries land debt) - 2-3 Sub-Funds (e.g., Alma Fund 1, Fund 2, Fund 3) - Each fund with own zone, own assets, own debt - Master Fund takes 30% revenue share - JV equity split per fund 2. Reconcile against Alma reference: - Master Fund FCFE IRR within 0.5% - Per-fund IRR within 0.5% - Consolidated returns within 1% Verification: - Master Holding mechanics validated - Reconciliation report saved | Not started
Q4 | End-to-end snapshot guards | Lock in regression coverage for all modules. Target outcome: 1. Add snapshot fixtures for each of M2-M11 covering: Sell, Operate, Lease, Hybrid, Master Holding, JV split, Multi-phase, Multi-scenario. 2. Single combined diff script: scripts/refm-snapshot-diff.ts. Exit 0 only if all module outputs match. 3. Documented as mandatory pre-commit gate going forward. Verification: - Diff exit 0 with current code - Intentional break: clear error message identifying which module diverged | Not started
L1 | Pre-launch hardening | Production hardening before launch. Target outcome: 1. Performance audit: Lighthouse + Vercel Speed Insights. Target FCP < 2s, LCP < 2.5s, CLS < 0.1. 2. Accessibility: keyboard nav, ARIA labels, color contrast WCAG AA. 3. Error boundaries on every route. 4. Loading states on all async operations. 5. Empty states on all lists/tables. 6. Mobile responsive: view-only mode acceptable for phones, full editing on tablets+. Verification: - Lighthouse scores reported - Manual a11y audit completed | Not started
L2 | Pricing tier integration | Re-introduce subscription-based feature gating. Target outcome: 1. Restore subscription system from Phase 5 admin cleanup. Build canAccess() resolver based on user's plan tier. 2. Plan tiers: Free (Module 1 + Excel/PDF basic), Professional (Modules 1-11 + Module 10 Collaborate), Enterprise (Module 13 formula export + whitelabel + Module 12 PPT). 3. Stripe / payment integration. Webhook syncs tier changes to user's plan field. 4. Wire UpgradePrompt buttons to checkout flow. Verification: - Free user sees lock on Modules 2-11 - Professional unlocks - Enterprise unlocks formula export | Not started
L3 | Launch | REFM public launch. Target outcome: 1. Remove Coming Soon mode in modeling hub. 2. Public registration enabled for app.financialmodelerpro.com. 3. Marketing site updated. 4. Launch announcement. Verification: - New user can register, sign in, access Module 1, complete setup, run Modules 2-11, export, upgrade to paid tier | Not started