## Architecture
REFM Platform: Architecture Reference
Locked decisions. Every prompt must comply with these. Version 2 (supersedes Modeling_Hub_Prompt.xlsx)
1. DATA HIERARCHY
Layers | 5 layers: Master Holding → Sub-Project (Fund) → Phase → Asset → Sub-Unit. Single-project users leave Master Holding null. Sub-Project = a fund / zone / standalone project. Phase = sequenced timeline chunk within a Sub-Project. Asset = building or operating entity. Sub-Unit = saleable/operable inventory within an asset.
Master Holding | Optional top-level entity owning master land, takes revenue share % from each Sub-Project, carries master debt for land acquisition. Has its own P&L, cashflow, returns. When present, Sub-Projects contribute equity (cash + land in-kind), pay revenue share, and roll up to Master Holding consolidation.
Sub-Project (Fund) | Independent financing unit. Has its own equity stack (cash + land in-kind), debt, scenarios, returns (FCFE IRR, DDM IRR, MOIC). Can have one or many Phases. Can stand alone (no Master Holding) or be part of a Master Holding.
Phase | Sequenced chunk with own Construction Start / Operations Start / Handover. Multiple Phases can overlap. Each Phase has its own capex curve, can have its own asset list. Phase-level financing is permitted but optional (most cases finance at Sub-Project level).
Asset | Building or operating entity. Has type (locked enum from list of 20, see section 2), category (Sell/Operate/Lease/Hybrid - drives form rendering), one or more Sub-Units. Has own land allocation, capex stack (9 categories), revenue stream(s).
Sub-Unit | Inventory unit. For Sell mode: 1BR/2BR/Studio/Branded Suite/Villa V1/V2 etc. For Operate mode: Twin Key/King Key/Suite. For Lease mode: optional split by floor or zone. Each Sub-Unit has area, count, price/rate, and may have its own pricing escalation.
Securitization | OUT OF SCOPE for v1. Not modeled. Defer to v2.
1A. AREA PROGRAM (Plot / Zone / Strategy / Sub-Unit physical hierarchy)
Plot | New entity between Phase and Asset. A Plot is a physical land parcel with: name, dimensions (length × width or area), Plot Area sqm, Max FAR, Max GFA (derived = Plot Area × Max FAR), Coverage % (footprint ratio), Footprint sqm (derived = Plot × Coverage), Public Area sqm (Plot − Footprint), Landscape %, Hardscape %, Number of Floors, Number of Podium Floors, Number of Typical Floors. A Phase can have one or many Plots. Each Plot has its own buildable envelope and FAR cap from regulator.
Zone (optional) | Optional sub-division of a Plot. A Plot can have one or many Zones. Each Zone has own dimensions, own Coverage %, own Floor count, own Podium GFA + Typical Floor GFA. Used when a single plot is split into mixed-use clusters (e.g., Project DAS Zone 1A is hotel+office+retail tower, Zone 1B is residences, Zone 2 is low-rise residential, Zone 3 is villas). When a Plot has only one Zone, UI hides the Zone layer.
Strategy allocation per Asset | Each Asset carries Primary Strategy (Develop & Sell / Develop & Lease / Develop & Operate) with Allocation % (default 100%), and optional Secondary Strategy with Allocation % (default 0%). Allocations sum to 100%. Strategy + allocation drive which revenue stream(s) apply at what proportion. Cleaner than current Sell/Operate/Lease/Hybrid enum: Hybrid = any asset with secondary > 0%.
Detailed area cascade per Asset | Asset-level area breakdown (replaces simple GFA → BUA → NSA chain). Per asset: Land Allocation %, Land Area, TBA (Total Built-Up Area), BUA Excluding (MEP & Basement), GFA, GSA / GLA (with GLA/GFA efficiency ratio per sub-unit), MEP Area, Basement Parking allocation, Landscape & Hardscape allocation. Plus building-level: Other Technical Floors, Back of House & Circulation. All driven by per-sub-unit ratios that aggregate up.
Sub-Unit schedule per Asset | Per Asset, schedule of Sub-Units: Studio / 1BR / 2BR / 3BR / Branded Suite / Twin Key / King Key / Villa V1/V2 etc. Each Sub-Unit row: % of Total BUA, BUA sqm, GFA sqm, GSA/GLA sqm, MEP allocation, Basement allocation, Average Unit Size sqm, Number of Units/Keys, Parking Bays per Unit. Auto-aggregates to Asset Total/Average row.
Parking calculation engine | Per residential Sub-Unit: Parking Bays/Unit ratio (typical: Studio 1.0, 1BR 1.0, 2BR 1.6, 3BR 2.0). Per commercial Asset: Parking Bays per 25 sqm of GFA (Hotels typically 1 bay per key or per 35 sqm GFA, Offices 1 bay per 25 sqm GFA, Retail 1 bay per 25 sqm GFA). Then: Surface Parking Area + Vertical Parking Area + Basement Parking Area with Bay Size sqm (typically 25 surface, 40 vertical, 44 basement) + Number of Basement Floors derived = Total Parking Bays / (Basement Floor Area × Basement Efficiency / Bay Size). Drives basement capex significantly.
Podium vs Typical Floor | Critical for tower-on-podium designs. Podium has higher Coverage % (typically 0.65-0.75) and houses retail/hotel/offices/amenities. Typical Floors have lower Coverage % (typically 0.45-0.65) and house residences. Calculated separately: Podium GFA = Footprint × Number of Podium Floors. Typical Floor GFA = Typical Floor Coverage × Plot × Number of Typical Floors. Sum = Total GFA per Plot.
2. ASSET TYPE CATALOG
Pre-built types (20) | Sell category: Branded Villas, Branded Apartments, High-end Villas, High-end Apartments, Class B Apartments. Operate category: Hotel 4-star, Hotel 5-star, Resort, Serviced Apartments, Senior Living, Student Housing. Lease category: Retail, Office, Industrial, Healthcare, Self-Storage, Data Center. Mixed/Special: Marina, Cinema, Mixed-Use.
Custom types | User can add custom asset types. Required fields: name (string), category (dropdown: Sell / Operate / Lease / Hybrid). Category drives form rendering, Sell shows units × price form, Operate shows occupancy × ADR form, Lease shows area × rate form, Hybrid shows multiple stream forms.
Category enum | Sell, Operate, Lease, Hybrid. Locked. Hybrid asset can have 2+ revenue streams (e.g., serviced apartments selling AND operating same units; mixed-use building leasing podium and operating hotel floors). Each stream is configured separately within the Hybrid asset.
Type → P&L mapping | Sell types use revenue recognition + receivables roll-forward. Operate types use full Uniform System of Accounts P&L (see section 6). Lease types use NOI = Revenue − OpEx. Hybrid types compose multiple.
3. CURRENCY
Single currency per project | v1 limitation. Set at Sub-Project creation. All values in that currency. Master Holding currency = Sub-Projects currency (must match).
Multi-currency | DEFERRED to v2.
4. SCENARIO SYSTEM
Three primary scenarios | Base / Management / Upside. Each is a named scenario stored as a delta over Base assumptions for: occupancy curves, ADR growth, sale velocity, down payment %, escalation, payment plan installments, rental growth, vacancy.
Additional scenarios | User can add unlimited additional named scenarios. UI surfaces the 3 primaries by default; user accesses extras via a 'More scenarios' menu.
Active scenario | Toggle in Topbar drives display. All KPIs, charts, exports reflect active scenario.
Sensitivity inputs | Per scenario, user can override: occupancy %, ADR growth %, ADR base, sale velocity (units sold per year curve), down payment %, escalation %, payment plan installments, rental growth %, vacancy %. Other inputs inherit from Base.
Final Dashboard scenario toggle | Module 11 dashboard has live scenario switcher. KPIs, charts, returns refresh on toggle without reload.
5. FINANCING STRUCTURE
Tranches | Up to 3 financing tranches per Sub-Project, with seniority order (1=most senior). Each tranche has: name, principal amount or % of capex, term, interest rate (fixed only for v1), drawdown schedule (linear / s-curve / custom %), repayment method (fixed / cash sweep / balloon), repayment start period. Standard pattern: Senior + Mezzanine + Equity.
Equity composition | Equity = Cash + Land In-kind. Both contribute to equity stack. Land in-kind value uses Land Value × parcel allocation. Cash equity drawdowns scheduled separately.
Interest | Fixed rate per tranche for v1. Floating (SAIBOR + premium) deferred to v2. Interest During Construction capitalizes per tranche toggle. Half-period interest convention on drawdowns.
Master Fund debt | If Master Holding exists, it can carry its own debt (typically for land acquisition) separate from Sub-Project debt. Master Holding interest expensed against Master Holding revenue share.
DSCR / ICR | Calculated and displayed per period. DSCR < 1.2x flagged amber, < 1.0x flagged red. Used for monitoring, not for sizing in v1.
Securitization | OUT OF SCOPE.
6. HOSPITALITY P&L (Uniform System of Accounts for the Lodging Industry, USAH)
Revenue | Departmental: Rooms (Occupied Nights × ADR), F&B (% of Rooms or Occupied × Guests/Room × Spend/Guest), Spa/Health Club (% of Rooms), Other (% of Rooms). ADR Growth Rate per year (compounding).
Departmental Expenses | Per department as % of departmental revenue. Defaults: Rooms 15-25%, F&B 50-60%, Spa 50%, Other 40%. User configurable per asset.
Departmental Income | Departmental Revenue − Departmental Expenses.
Undistributed Operating Expenses | % of total revenue: A&G (Admin & General), Group Services, Marketing/Sales, POM (Property Ops & Maintenance), Utilities. User configurable per asset.
Gross Operating Profit (GOP) | Departmental Income − Undistributed.
Base Management Fee | % of total revenue. User configurable. Defaults vary 1.5-3%.
Adjusted GOP | GOP − Base Management Fee.
Fixed Expenses | Incentive Management Fee (% of Adjusted GOP), Insurance (% of revenue), Replacement Reserve / FF&E Reserve (% of revenue), Property Tax / Land Lease (if applicable).
EBITDA after FF&E Reserve | Final operating output. Reported with PAR (per available room) and POR (per occupied room) KPIs.
Land Lease | Optional toggle per asset. Deducted as separate line above EBITDA when active. Has own growth rate.
7. REVENUE MODES (3 modes + hybrid)
SELL mode | Inventory: Sub-Units × Price/Unit OR Area sqm × Price/sqm. Indexation factor compounding annually. Pre-sale velocity schedule (% sold per year, sums to ≤100%). Down Payment % per year. Payment plan after DP (installments over N years). Cash collection profile per cohort (2D matrix: Year-N sales generate collections in Year N, N+1, N+2 per installment schedule). Revenue Recognition profile separate from cash collection (over construction period). Sales During Operation (residual unsold sold post-handover at indexed price). Receivables Roll-Forward: Opening + New Sales − Collected = Closing. Sales Commission % deducted from revenue.
OPERATE mode (full USAH per section 6) | Inventory: Keys/Units × Days/Year × Occupancy %. Revenue: Occupied × ADR. F&B/Spa/Other as % of Rooms. Operations Start Year per asset (not project-level). Multi-scenario occupancy curves.
LEASE mode | Inventory: Total Lease Area sqm. Loading factor: Gross × (1−Loading%) = Rentable. Vacancy %: Rentable × (1−Vacancy) = Leased. Revenue = Leased × Rent SAR/sqm/year. Rental Growth Rate compounding. OpEx % of revenue (or itemized). NOI = Revenue − OpEx.
HYBRID mode | Asset has 2+ revenue streams running simultaneously. Common case: serviced apartments (Sell + Operate same units, sold post-handover). Mixed-use building (Lease podium + Operate hotel floors). Each stream configured separately, all roll up to single asset P&L.
8. CAPEX STACK (per Asset)
9 line categories | 1. Land Cost (parcel area × rate × active flag). 2. Hard Construction (broken by Sub-Unit, sqm × rate or per-key). 3. Construction Parking (Parking sqm × rate). 4. Infrastructure (Land sqm × % × rate). 5. Landscaping (Land sqm × % × rate). 6. Pre-operating (% of Hard + Infra + Landscape). 7. Professional Fee (% of Hard + Parking). 8. Commission (% of Pre-sale + Post-operation revenue, creates loop). 9. Contingency (% of Hard + Parking).
Capex phasing | Each cost category has its own % allocation across construction periods, summing to 100%. Standard patterns: Land 100% Y1, Hard 30/30/30/10 over 4 years, Pre-op spread per asset operations curve, Commission tied to revenue schedule.
Cost methods | fixed, rate_total_allocated, rate_net_developable, rate_roads, rate_gfa, rate_bua, percent_base (loops over selectedIds), percent_total_land, percent_cash_land, percent_inkind_land. Existing Module 1 supports these, preserve.
Project-scope vs asset-scope | Cost item has scope='asset' (belongs to one asset) or scope='project' (allocated across assets via direct_cost share or gfa share). Existing Module 1 V14, preserve.
Dev Fee circular | When devFeeMode='include', dev fee total = base × rate / (1 − rate). Existing V14 logic, preserve.
9. AI AGENTS
Research agent | Pulls market intel for a city: population, demographics, GDP, key sectors, infrastructure, transport, regulations. Anthropic SDK + web search tool. Cached per city for 7 days.
Market Rates agent | Pulls current ADR / RevPAR / Cap Rates / Rental rates / Construction costs by (city, asset_type) pair. Anthropic SDK + web search tool. Cached per (city, asset_type) for 7 days.
User override | Every agent-suggested value has user override input. User-set values take priority. Agent values are suggestions stored separately for audit.
Cost control | Cache aggressively. Single agent run per (key, day) per user. Display 'Last refreshed N days ago' with manual refresh button.
10. EXPORT
Excel Static | Token-driven exceljs. FAST color convention (blue inputs / black formulas / green cross-sheet / red external / yellow assumptions). Built. Phase 2 of design tokens shipped.
Excel Formula | Full formula-driven workbook with named ranges, XIRR/XNPV, scenario switches via INDIRECT, sensitivity tables. Enterprise tier. Build in Module 13.
PDF Basic | @react-pdf/renderer. Token-driven. Built. Phase 3 shipped.
PDF Whitelabel | Per-client branded PDF (logo, color override, custom footer). Enterprise tier. Build in Module 13.
Investment Memorandum (PDF + PPT) | Module 12. Sections: Cover, Exec Summary, Highlights, Market, Location, Project Description, Development Program, Financial Summary, Investment Structure, Comparables, Risks, Macro, Developer Profile. PDF + PPT formats. v1 only static export, in-app interactive view deferred.
11. FINAL DASHBOARD (Module 11)
Purpose | Project home screen with live KPIs, charts, scenario switcher. Becomes the default view after Module 1 setup is complete.
KPIs | IRR (FCFE + DDM), MOIC, NPV at user-set discount rate, Payback Year, Development Margin %, Profit on Cost %, Cash-on-Cash, DSCR average, LTC, LTV, Equity Multiple.
Charts | Cashflow waterfall (capex → revenue → debt service → equity returns), Sources & Uses bar, Returns by year line, Sensitivity tornado, Breakeven occupancy chart, Capital stack pie, Distribution timeline.
Scenario switcher | Top-of-page toggle for Base / Management / Upside / Custom. All metrics + charts refresh live.
Sensitivity tables | NPV vs discount rate, IRR vs occupancy, IRR vs sale price, IRR vs ADR. 2D tables with conditional formatting.
Breakeven analysis | Per asset: occupancy that breaks even on EBITDA / Interest / Debt Service. For Sell: sale price that breaks even on equity invested.
12. DESIGN TOKENS & FAST CONVENTION (locked from Phase 1-4)
Token system | src/hubs/modeling/design-tokens/. Universal across all platforms. Pulled from CMS header_settings.brand_color (currently #1E3A8A navy) for chrome. FAST cells encoded as semantic tokens.
FAST cell rules | Inputs: blue text on white background (--color-navy-pale + --color-navy). Formulas: black text on light grey (--color-grey-pale + --color-heading). Linked: green text. External: red text. Assumptions: yellow background. ABSOLUTE: no hardcoded hex anywhere outside token files.
Cell primitives | InputCell, FormulaCell, LinkedCell, AssumptionCell, SectionHeader, KpiCard, TableHeader. Use these, do not write inline styles.
Light + Dark mode | All components must work in both. Light = white surfaces. Dark = navy-tinted surfaces. Brand chrome stays navy in both. Test every screen in both modes.
13. PERSISTENCE
Current state | localStorage key refm_v2. JSON-serialized. Per-project versioning. NO Supabase persistence yet.
v1 target | Move REFM project storage to Supabase. New tables: refm_projects, refm_project_versions. Per-user RLS. localStorage becomes cache only. Migration: existing localStorage data uploads to Supabase on next save.
Schema migration policy | Every breaking schema change has a migrator function. Loaded versions auto-upgrade to current schema. Document in CLAUDE-DB.md.
14. FOLDER STRUCTURE
Hubs structure | src/core/ (DB, types, env, formatters), src/shared/ (auth, email, newsletter), src/hubs/main/, src/hubs/training/, src/hubs/modeling/. Modeling Hub: src/hubs/modeling/platforms/refm/ (and reserved bvm/, fpa/, etc.).
REFM internal structure | src/hubs/modeling/platforms/refm/components/ (UI), components/cells/ (cell primitives), components/modules/ (Module N tabs), lib/modules/ (calculation engines per module), lib/exporters/ (excel + pdf builders), lib/agents/ (research + market-rates), lib/state/ (Zustand store after refactor).
ESLint boundary | Enforced. modeling cannot import from training. core/shared shared by all. Already in place.
15. PROCESS RULES (carry over from Phase 1-4)
Ahmad → Claude (chat) → Claude Code | Ahmad describes task. Chat-Claude writes prompt. Ahmad pastes to Claude Code. Code executes, commits, pushes, reports.
Per-phase commit | One logical commit per phase. Type-check + build pass before commit.
Snapshot diff | Mandatory for any change to Module 1 calculation files. scripts/module1-snapshot-diff.ts must exit 0.
No em dashes | Use commas / colons / periods / parentheses / and-or instead. Carries to all written output, code comments, UI strings, exports.
Eyeball verification | After every UI commit, Ahmad verifies in browser before approving next phase. Light + dark both checked.
Stop at boundaries | Each phase pauses for confirmation. No multi-phase scope creep without explicit approval.

## Tracker
REFM Platform: Build Tracker | [7 empty] | Done
Sequenced execution plan. Each phase pauses for verification before next. | [7 empty] | Not Started
In Progress
Ph# | Phase | Deliverable | Status | Start Date | Completion Date | Hours | Dependencies
F0 | Folder restructure | src/hubs/, src/core/, src/shared/, ESLint boundaries, path aliases | Done |  |  |  | Pre-existing
F1 | Design tokens system | src/hubs/modeling/design-tokens/, FAST cells, light+dark, Tailwind wiring, README | Done |  |  |  | Pre-existing
F2 | Excel exporter token retrofit | lib/exporters/excel.ts pure builder, FAST cell colors, fixture script | Done |  |  |  | F1
F3 | PDF exporter token retrofit | lib/exporters/pdf.ts pure builder, FAST cell colors, fixture script | Done |  |  |  | F1
F4 | Module 1 snapshot guard | tests/fixtures/module1-reference.json + scripts/module1-snapshot-diff.ts | Done |  |  |  | F1
F5 | REFM component token retrofit | All 15 REFM files. Phase 4.1-4.15. Hex/rgba grep zero across folder. | Done |  |  |  | F1, F4
F6 | Modeling Hub sidebar shell | /modeling/dashboard sidebar layout, CMS logo, dark mode toggle | Done |  |  |  | F1
F7 | REFM Topbar dark mode toggle | Independent localStorage key, scoped to .app-shell | Done |  |  |  | F5
F8 | Module name editing | ProjectModal edit mode wired, pencil button on Overview + Projects | Done |  |  |  | F5
M1.R | Module 1 typed-shape refactor | Lift hardcoded asset enum to AssetClass[]; replace single-phase model with Phase[]; normalize residentialCosts/hospitalityCosts/retailCosts into a single costs[] keyed by assetId. Calculations bit-identical (snapshot diff exit 0). Persistence migrator handles old refm_v2 shape. | Done | 2026-05-02 | 2026-05-02 | 8 | F4 snapshot
M1.5 | Module 1 hierarchy upgrade | Add Master Holding (optional) → Sub-Project → Phase → Asset → Sub-Unit support to Module 1. UI gains Hierarchy tab (5th tab) for managing layers. Existing Timeline/Area/Costs/Financing tabs remain but operate per-Phase. | Done | 2026-05-02 | 2026-05-02 | 12 | M1.R
M1.5b | Hierarchy UX polish | First-time empty state with guided CTA. Inline tooltips on each layer (Master Holding, Sub-Project, Phase, Asset, Sub-Unit) explaining what they are and when to use. Optional Quick Setup wizard for single-project / single-phase users (collapses 5 layers into one form). Clearer visual hierarchy (parent-child indentation, expand/collapse, breadcrumb on selection). Empty-state illustrations at each level. Light + dark verified. | Done | 2026-05-02 | 2026-05-02 | 6 | M1.5
M1.6 | Module 1 Supabase persistence | Migrate from localStorage to Supabase tables refm_projects, refm_project_versions. Per-user RLS. localStorage becomes cache. Migrator uploads existing data on first save. | Done | 2026-05-02 | 2026-05-02 | 6 | M1.5
M1.7 | Module 1 Area Program | Add Plot and optional Zone entities between Phase and Asset. Add Strategy allocation per Asset (Primary + Secondary with %). Add detailed area cascade per Asset (TBA, BUA Excl, GFA, GSA/GLA, MEP, Basement, Landscape, Hardscape, Other Technical, Back of House). Add Sub-Unit schedule with parking ratios. Add Podium vs Typical Floor split. Add parking calculation engine (surface, vertical, basement). New 'Area Program' tab in Module 1. | Done | 2026-05-02 | 2026-05-02 | 16 | M1.6
M1.8 | Smart Project Creation Wizard | 3-step wizard at project creation. Asks structure questions (fund/single, phases, plots, project type, assets). Pre-creates hierarchy matching answers. User lands in populated workspace, not empty Hierarchy tab. Progressive disclosure: hidden layers reveal via "+ Add Phase / Plot / Enable Master Holding" buttons. | Done | 2026-05-03 | 2026-05-03 | 8 | M1.7
M2.1 | Module 2, Revenue: Sell stream | Per-asset Sell mode: Sub-Units × price grid, indexation, pre-sale velocity schedule, down payment %, payment plan installments, cash collection cohort matrix, revenue recognition profile, sales during operation, receivables roll-forward, sales commission. Outputs to Module1Exports interface for downstream modules. | Not started |  |  | 14 | M1.7
M2.2 | Module 2, Revenue: Operate stream (USAH) | Per-asset Operate mode: Keys × Days × Occupancy = Occupied, ADR + ADR growth, F&B as % of Rooms or per-occupied, Spa, Other. Departmental Revenue + Departmental Expenses + Departmental Income + Undistributed (A&G/Marketing/POM/Utilities) + GOP + Base Mgmt Fee + Adjusted GOP + Fixed (Insurance/FF&E Reserve/Property Tax/Land Lease) + Incentive Mgmt Fee. EBITDA after FF&E Reserve. PAR + POR KPIs. Multi-scenario occupancy curves. | Not started |  |  | 12 | M1.7
M2.3 | Module 2, Revenue: Lease stream | Per-asset Lease mode: Total Lease Area, Loading factor, Vacancy %, Rent/sqm, Rental Growth Rate, OpEx (% of revenue or itemized). NOI = Revenue − OpEx. | Not started |  |  | 6 | M1.7
M2.4 | Module 2, Revenue: Hybrid composition | Hybrid asset combines 2+ streams (e.g., serviced apartments Sell + Operate same units). Streams configured separately, roll up to single asset P&L. Common patterns pre-built: Serviced Apartments, Mixed-Use Building (Lease podium + Operate hotel). | Not started |  |  | 6 | M2.1, M2.2, M2.3
M2.5 | Module 2 UI tabs | Tabs per Asset: Stream config, Pricing/ADR/Rent, Schedules (velocity/occupancy/vacancy), Outputs (per-period revenue + collections). FAST cells throughout. | Not started |  |  | 10 | M2.1-M2.4
M2.6 | Module 2 sample fixture + snapshot guard | Add Module 2 to scripts/snapshot-diff. Cover Sell + Operate + Lease + Hybrid sample assets. Reference numbers verified against MAAD + Hospitality fixture patterns. | Not started |  |  | 4 | M2.5
M3 | Module 3, Operating Expenses | Beyond hospitality direct opex (handled in M2.2): corporate overhead (e.g., New Company Costs SAR 2M/year), Zakat/Tax %, Working Capital days. Per-period schedules. Outputs ready for M5 financial statements. | Not started |  |  | 8 | M2
M4.1 | Module 4, Project IRR / Equity IRR | Unlevered Project IRR (capex out, NOI/EBITDA in, terminal value in). Levered Equity IRR (after debt service). Per Sub-Project. Per Master Holding (when present). | Not started |  |  | 6 | M2, M3
M4.2 | Module 4, FCFE + DDM dual returns | FCFE IRR/MOIC and DDM IRR/MOIC computed in parallel per Sub-Project. Shareholder split when JV (e.g., 65/35) drives per-investor returns. Match Hospitality + Alma model patterns. | Not started |  |  | 6 | M4.1
M4.3 | Module 4, NPV, MOIC, Payback, Margins | NPV at user-discount-rate, MOIC = total distributions / total equity, Payback Year (cumulative cash crosses zero), Development Margin = (Revenue − Cost) / Revenue, Profit on Cost = (Revenue − Cost) / Cost, Cash-on-Cash annual. | Not started |  |  | 4 | M4.1
M4.4 | Module 4, DSCR, ICR, LTC, LTV per period | Coverage and leverage ratios per period. DSCR < 1.2x amber, < 1.0x red. Display in returns dashboard. | Not started |  |  | 4 | M4.1
M4.5 | Module 4, Terminal Value | Terminal Value computed at terminal year per asset: capitalized NOI / cap rate, OR multiple × final-year EBITDA, OR exit price. User picks method per asset. Selling Cost % deducted. | Not started |  |  | 4 | M4.1
M5.1 | Module 5, P&L statement | Per-period P&L per Sub-Project: Revenue (by stream) → COGS (capex amortized over recognized revenue for Sell, none for Operate/Lease) → Gross Profit → OpEx → EBITDA → D&A → EBIT → Interest → EBT → Tax/Zakat → Net Income. | Not started |  |  | 6 | M2, M3, M4
M5.2 | Module 5, Cash Flow statement | Per-period CF per Sub-Project: Operating CF (EBITDA − Tax − ΔWC) + Investing CF (Capex, FF&E Reserve) + Financing CF (Equity drawdown, Debt drawdown, Debt repayment, Interest paid, Dividends) = Net Change. Master Holding consolidated CF when applicable. | Not started |  |  | 6 | M5.1
M5.3 | Module 5, Balance Sheet | Per-period BS: Land + WIP + Receivables + Cash = Loan + Payables + Equity + Retained Earnings. Reconciles to CF. | Not started |  |  | 6 | M5.2
M5.4 | Module 5, Cash Sweep waterfall | Available cash − Min cash required = Distributable to dividend. Per scenario. Master Holding consolidation when applicable. | Not started |  |  | 4 | M5.2
M6 | Module 6, Reports & Visualizations | Tabular and chart views of Module 4 + Module 5 outputs. Charts: Cashflow waterfall, Sources & Uses, Returns by year, Capital stack. Per-period drill-down. Print-ready layouts. | Not started |  |  | 8 | M5
M7.1 | Module 7, Scenario engine | Scenario delta storage. 3 primary (Base/Management/Upside) + unlimited custom. Each scenario stores deltas for: occupancy curves, ADR growth, sale velocity, DP%, escalation, payment plan, rental growth, vacancy. Active scenario toggle drives display. | Not started |  |  | 8 | M2
M7.2 | Module 7, Sensitivity tables | 2D sensitivity: NPV vs discount rate, IRR vs occupancy, IRR vs sale price, IRR vs ADR. Conditional formatting. Tornado charts. | Not started |  |  | 6 | M7.1, M4
M7.3 | Module 7, Breakeven analysis | Per asset: solve for occupancy that hits EBITDA / Interest / Debt Service breakeven. For Sell assets: solve for sale price that breaks even on equity invested. Match Hospitality model breakeven format. | Not started |  |  | 6 | M4
M8.1 | Module 8, Portfolio rollup | Master Holding rollup view across all Sub-Projects: consolidated revenue, EBITDA, capex, debt, returns. Per-Sub-Project comparison table. Tracks Hospitality 7-project model + Alma 7-fund model patterns. | Not started |  |  | 8 | M5
M8.2 | Module 8, Cross-project allocation | Project-scope cost allocation across Sub-Projects (master infrastructure, master marketing, master overhead) by share rules (revenue share, capex share, gfa share). | Not started |  |  | 4 | M8.1
M9.1 | Module 9, Research agent | Anthropic SDK + web search. City market intel: population, demographics, GDP, sectors, infra, regs. 7-day cache per city. | Not started |  |  | 8 | M2
M9.2 | Module 9, Market Rates agent | Anthropic SDK + web search. ADR/RevPAR/Cap Rates/Rental rates/Construction costs by (city, asset_type). 7-day cache per pair. | Not started |  |  | 8 | M9.1
M9.3 | Module 9, Agent UI integration | Per asset/parcel, 'Suggest from market' button calls relevant agent, displays result with override input. User-set values priority. Audit log of suggested vs accepted values. | Not started |  |  | 6 | M9.2
M10 | Module 10, Collaborate (Pro tier) | Multi-user project access, role-based permissions (already has RBAC modal), comment threads, change history, share link. Defer post-launch if scope tight. | Optional v1.5 |  |  | 16 | M1.6 Supabase
M11.1 | Module 11, Final Dashboard layout | Project home screen replacing current Overview. Top scenario switcher. KPI grid (IRR FCFE, IRR DDM, MOIC, NPV, Payback, Dev Margin, PoC, CoC, DSCR avg, LTC, LTV, Equity Multiple). | Not started |  |  | 6 | M4, M5, M7
M11.2 | Module 11, Charts package | Cashflow waterfall, Sources & Uses bar, Returns by year line, Sensitivity tornado, Breakeven occupancy chart, Capital stack pie, Distribution timeline. Recharts. | Not started |  |  | 8 | M11.1
M11.3 | Module 11, Live scenario switcher | Toggle scenarios, all KPIs and charts refresh without reload. Custom scenario picker for non-primary scenarios. | Not started |  |  | 4 | M11.1, M7.1
M12.1 | Module 12, IM PDF builder | Sections: Cover, Exec Summary, Highlights, Market, Location, Project Description, Development Program, Financial Summary, Investment Structure, Comparables, Risks, Macro, Developer Profile. @react-pdf/renderer. Token-driven. | Not started |  |  | 12 | M11
M12.2 | Module 12, IM PPT builder | Same content, PPT format. pptxgenjs library. Token-driven. | Not started |  |  | 8 | M12.1
M13.1 | Module 13, Excel formula export (Enterprise) | Full formula-driven workbook: named ranges, XIRR/XNPV, scenario switch via INDIRECT, 2D sensitivity tables, all Module 5 statements. Replicates entire model in Excel. | Not started |  |  | 16 | M5, M7
M13.2 | Module 13, PDF Whitelabel (Enterprise) | Per-client branded PDF: logo, color override, custom footer/header. Reads from client_branding table. | Not started |  |  | 6 | F3
Q1 | Integration QA, Hospitality fixture | Build the 7-project hospitality model from earlier (Project 1-7, hotel + retail + office) end-to-end through the platform. Reconcile outputs against the Excel reference. | Not started |  |  | 10 | M1-M11
Q2 | Integration QA, MAAD fixture | Build the 5-asset 3-phase MAAD residential + hotel model end-to-end. Reconcile against Excel. | Not started |  |  | 10 | M1-M11
Q3 | Integration QA, Alma fixture | Build a 7-fund Master Holding + sub-funds + zones model (subset of full Alma, Master Fund + 2-3 sub-funds is enough to validate hierarchy). Reconcile. | Not started |  |  | 12 | M1-M11
Q4 | End-to-end snapshot guards | Add fixtures + snapshot diffs for M2-M11 covering all calculation paths. Mandatory exit 0 before any future commit touching modules. | Not started |  |  | 6 | Q1-Q3
L1 | Pre-launch hardening | Performance audit, accessibility pass, error boundaries, loading states, empty states, mobile-responsive checks for view-only. | Not started |  |  | 8 | Q4
L2 | Pricing tier integration | Re-introduce subscription system removed in Phase 5 admin cleanup. Plan-based feature gating restored. Stripe / payment integration. | Not started |  |  | 12 | L1
L3 | Launch | Public REFM availability for app.financialmodelerpro.com modeling hub. Module 10 (Collaborate) post-launch v1.5. | Not started |  |  | 4 | L2
| TOTAL |  |  |  |  | 348

## Prompts
REFM Platform: Paste-Ready Prompts
Each prompt is one execution unit for Claude Code. Read the Architecture sheet first. Comply with all 15 sections. Snapshot diff exit 0 mandatory for any change touching Module 1 calculations.
Ph# | Phase | Prompt | Status | Start Date | Completion Date
M1.R | Module 1 typed-shape refactor | Refactor Module 1 to support multi-asset and multi-phase data shape without changing calculation outputs. Read Architecture sheet sections 1, 2, 8, 14 before starting. Target outcome: 1. Replace the hardcoded `'residential' ¦ 'hospitality' ¦ 'retail'` string union with a typed AssetClass[] array. Each asset has: id, name, type (from 20 pre-built or custom string), category ('Sell' ¦ 'Operate' ¦ 'Lease' ¦ 'Hybrid'), allocationPct (% of project GFA), deductPct, efficiencyPct. 2. Replace the single Construction-Operations timeline with a Phase[] array. Each phase has: id, name, constructionStart, constructionPeriods, operationsStart, operationsPeriods, overlapPeriods. Single-phase users have one phase. Multi-phase users add more. 3. Normalize the parallel `residentialCosts[] / hospitalityCosts[] / retailCosts[]` arrays into a single `costs[]` keyed by `assetId` (and optional `phaseId` for phase-specific costs). 4. Lift state from 30+ useState hooks in RealEstatePlatform.tsx into a Zustand store at `src/hubs/modeling/platforms/refm/lib/state/module1-store.ts`. Store exposes typed selectors and actions. Component reads via selectors. 5. Persistence migrator: on load, detect old refm_v2 shape (3 hardcoded asset arrays) and convert to new shape (1 normalized assets[] + 1 normalized costs[] + 1 phases[] with single phase). Preserve all data. 6. Calculations bit-identical. Snapshot diff `npx tsx scripts/module1-snapshot-diff.ts` must exit 0 against existing baseline. Constraints: - Do not introduce new calculations. Only restructure data and adapt existing calc functions to read from new shape. - buildAssetFinancing, calculateItemTotal, distributeCost, getAreas, allocateToAssets, calcItemTotalV14, getAssetDirectCost all preserve their signatures externally; internally they iterate the new assets[] array. - Same-for-all mode preserved as a UI/state preference, propagating non-land cost lines across all assets in costs[]. - All 4 Module 1 tabs (Timeline / Area / Costs / Financing) continue rendering correctly, in light + dark. - FAST cell convention preserved. Verification: - Snapshot diff exit 0 - Type-check + build pass - Manually: load existing project, verify all numbers identical - Eyeball Module 1 in light + dark One commit. Push to main. | Done | 2026-05-02 | 2026-05-02
M1.5 | Module 1 hierarchy upgrade | Add the 5-layer hierarchy to Module 1. Read Architecture sheet section 1 before starting. Target outcome: 1. New types: MasterHolding (optional), SubProject, Phase, Asset, SubUnit. SubProject has: id, name, currency, masterHoldingId (nullable), revenueShareToMaster (% if linked to master). 2. New "Hierarchy" tab in Module 1 (5th tab, becomes default landing of Module 1). UI: tree view of MasterHolding (optional) → SubProjects → Phases → Assets → SubUnits with create/edit/reorder controls. 3. Existing tabs (Timeline / Area / Costs / Financing) operate within a selected Phase context. Phase selector at top of these tabs. 4. SubUnit: per-asset inventory with name, count or area, price/rate (auto-driven by asset category Sell/Operate/Lease). 5. Master Holding: optional. When present, has its own land cost, debt, revenue share % from sub-projects, P&L, returns. UI shows separate "Master Holding" entity in Hierarchy tab. 6. Persistence: extend Zustand store and Supabase schema (preview only, actual Supabase migration in M1.6). Migrator handles old single-project shape. Constraints: - Single-project users (no Master Holding, one Sub-Project, one Phase) get a streamlined UX. Master Holding panel hidden until enabled. Multi-phase users see Phase selector. Default new project: 1 Sub-Project + 1 Phase + empty assets array. - Snapshot diff still passes for the single-phase fixture. - FAST cells throughout new Hierarchy tab. Verification: - Snapshot diff exit 0 (single-phase legacy fixture) - New fixture for multi-phase + multi-asset case added to tests/fixtures/ - Type-check + build pass - Eyeball: create a 3-phase project, add assets to each phase, switch phases, verify isolation | Done | 2026-05-02 | 2026-05-02
M1.5b | Hierarchy UX polish | Polish the Hierarchy tab UX for first-time users. The 5-layer structure is correct but currently feels heavy on first visit. Read Architecture sheet sections 1, 1A before starting. Reference Phase M1.5 Module1Hierarchy.tsx for current implementation. Target outcome: 1. First-time empty state. When project has zero Sub-Projects (brand new project, just created), show a centered card with: - Title: "Set up your project structure" - Two CTA buttons side by side: - "Quick Setup" (primary, navy button) - opens wizard - "Manual Setup" (secondary, outline button) - shows current Hierarchy tree directly - Brief 1-line description under each button explaining when to use which. 2. Quick Setup wizard. Modal-style multi-step form for single-project / single-phase users (90% case): - Step 1: Sub-Project basics (name, currency, location, status) - Step 2: Timeline (construction periods, operations periods, overlap) - Step 3: First Asset (asset type from 20 pre-built dropdown, category auto-derived, allocation %, deduct %, efficiency %) - Step 4: Sub-Units for that asset (skip option for users who want to add later) - Final: "Create" button. Wizard creates Sub-Project + 1 Phase + 1 Asset + Sub-Units (if any) in one transaction. - User can skip wizard at any step and switch to Manual mode (preserves what's been entered). - Available again later via "Add Sub-Project" button if user wants to add another sub-project via wizard. 3. Inline tooltips on each layer label. Hover the layer label or click an info icon to see: - Master Holding: "Optional. Use when you have multiple Sub-Projects under one parent entity (e.g., a real estate fund holding 7 funds, each with own land + debt + returns). Most projects skip this." - Sub-Project: "An independent financing unit. One Sub-Project = one fund / project / standalone development. Has its own equity, debt, returns. Most users have just 1 Sub-Project." - Phase: "A sequenced timeline chunk within a Sub-Project. Most projects have 1 Phase. Add more Phases for staged developments where Phase 2 starts construction years after Phase 1." - Asset: "A building or operating entity. One asset = one building or one operating unit type (e.g., 5-Star Hotel, Branded Apartments Tower 1, Retail Podium)." - Sub-Unit: "Inventory inside an Asset. For Sell: 1BR / 2BR / Branded Suite. For Operate: Twin Key / King Key. For Lease: optional split by floor or zone." 4. Visual hierarchy clarity: - Increase indentation per level (currently subtle, needs to be more obvious) - Add expand/collapse chevrons on each level (Sub-Project / Phase / Asset). Default expanded. - Sticky breadcrumb at top when scrolling deep ("FMP Mixed-Used > Phase 1 > Residential") - Subtle background tint per level to reinforce hierarchy (Sub-Project bg navy-pale, Phase bg lighter, Asset bg lightest) 5. Empty-state cards at each level when sub-items missing: - Sub-Project with no Phases: "+ Add first Phase" centered card with brief explainer - Phase with no Assets: "+ Add first Asset" centered card with type picker preview - Asset with no Sub-Units: existing "+ Add Sub-Unit" stays but adds 1-line hint above it 6. Page header context. Top of Hierarchy tab adds: - Quick stats line: "1 Sub-Project, 1 Phase, 3 Assets, 0 Sub-Units" - "Switch to Quick Setup" link (always available, not just empty state) Constraints: - Snapshot diff exit 0 (no calc changes, only UI) - Type-check + build pass - FAST cells throughout (no hardcoded colors) - Light + dark mode both work - Keyboard navigable (tab through wizard steps, Esc to close) - Accessible: tooltips have aria-label, wizard is screen-reader friendly Verification: - Snapshot diff exit 0 - Eyeball: create new project, walk through Quick Setup wizard end-to-end. Then create another project, use Manual Setup. Then open existing migrated project, verify breadcrumb + indentation + tooltips read correctly. Split into 4-6 commits, same per-commit verify+push cadence. | Done | 2026-05-02 | 2026-05-02
M1.6 | Module 1 Supabase persistence |  | Done | 2026-05-02 | 2026-05-02
M1.7 | Module 1 Area Program | Read Architecture sheet sections 1, 1A before starting. Reference Phase M1.5 Module1Hierarchy.tsx for current implementation. | Done | 2026-05-02 | 2026-05-02
M1.8 | Smart Project Creation Wizard | # Phase M1.8: Smart Project Creation Wizard ## Purpose Replace the current "blank Hierarchy tab" first experience with a guided wizard that asks 3-5 simple questions and pre-creates the project structure. User lands in a populated workspace, not an empty 5-layer tree. ## Problem We Are Solving Current flow: user creates project, lands on Hierarchy tab, sees 5 empty layers (Master Holding, Sub-Project, Phase, Plot, Asset, Sub-Unit), feels overwhelmed. New flow: user answers 3 questions during creation, lands in pre-populated workspace with structure already matching their needs. 90% of users (single project, single phase, single plot, 2-3 assets) never see Master Holding or multi-plot complexity unless they explicitly opt in later. ## Reference Read REFM_Build_Prompts_v2.1.xlsx Architecture sheet sections 1, 1A, 2 before starting. ## Target Outcome ### 1. Replace current "+ New Project" button behavior Currently the New Project button in Projects screen creates an empty project and routes to Hierarchy tab. Change it to open a 3-step wizard modal. ### 2. Wizard Step 1: Project Basics Inputs: - Project Name (required) - Location (required, e.g., "Riyadh, Saudi Arabia") - Currency (default SAR, dropdown from common currencies) - Model Type (radio: Annual / Monthly, default Annual) - Project Start Date (default today + 6 months) - Status (radio: Draft / Active, default Draft) Validation: Name and location required. Show "Continue" disabled until both filled. ### 3. Wizard Step 2: Project Structure Three questions with smart defaults: **Question 1: Is this part of a fund or portfolio?** - Toggle (default OFF) - If ON: enables Master Holding layer in Hierarchy tab. If OFF: Master Holding hidden by default (user can enable later from Hierarchy tab). **Question 2: How many phases?** - Radio: "Single Phase (most projects)" / "Multiple Phases (staged development)" - Default: Single Phase - If Multiple: ask "How many?" with number input (2-10). **Question 3: How many plots?** - Radio: "Single Plot" / "Multiple Plots (large land bank)" - Default: Single Plot - If Multiple: ask "How many?" with number input (2-20). ### 4. Wizard Step 3: Assets Based on user's project type selection, pre-fill suggested assets. **First, ask Project Type:** - Radio: Residential / Hospitality / Retail / Mixed-Use / Office / Custom - Default: Mixed-Use **Then suggest assets based on type:** ¦ Project Type ¦ Default Assets ¦ ¦--------------¦----------------¦ ¦ Residential ¦ 1 asset: "Residential Tower" (High-end Apartments, Sell, 100%) ¦ ¦ Hospitality ¦ 1 asset: "Hotel" (Hotel 5-star, Operate, 100%) ¦ ¦ Retail ¦ 1 asset: "Retail Center" (Retail, Lease, 100%) ¦ ¦ Office ¦ 1 asset: "Office Tower" (Office, Lease, 100%) ¦ ¦ Mixed-Use ¦ 3 assets: Residential Tower (Sell, 50%), Hotel (Operate, 30%), Retail Podium (Lease, 20%) ¦ ¦ Custom ¦ Empty list, user adds manually ¦ User can edit/add/remove assets in this step. For each asset row: - Name (editable) - Type dropdown (20 pre-built + Custom option) - Category (auto-derived from type, or user-set if Custom) - Allocation % (auto-balances to 100 across all assets) - Remove button (if more than 1 asset) - "+ Add Asset" button below Validation: Total allocation must = 100%. Show "Create Project" disabled until valid. ### 5. On "Create Project" Create the project with: - Sub-Project: "Main" (or user-named in Step 1) - Phase 1 (and Phase 2, Phase 3 if user picked Multiple Phases) - Plot 1 (and Plot 2... if user picked Multiple Plots) - Assets pre-created per Step 3 list, all bound to Phase 1 + Plot 1 by default - Single sub-unit per asset auto-created with placeholder values: - Sell: 1 unit, Unit Size = 100 sqm, Price = 0 (user fills later) - Operate: 1 key/unit, quantity = 1 (user fills later) - Lease: 1 area unit, area = 0 (user fills later) - Master Holding: NOT created unless Step 2 Question 1 was ON - Routes to Area Program tab (not Hierarchy tab) since structure is already set up ### 6. Hierarchy Tab Polish When Hierarchy tab is opened on a wizard-created project: - Hide layers user said they don't need (Master Holding, multi-phase complexity, multi-plot complexity) - Show only their actual structure - Top of Hierarchy tab: 3 action buttons always visible - "+ Add Phase" (creates Phase 2, etc.) - "+ Add Plot" (creates Plot 2, etc.) - "Enable Master Holding" toggle (turns on the Master Holding layer if user wants to convert to fund structure later) ### 7. Edit Project Structure Later When user clicks "Enable Master Holding" or "+ Add Phase" or "+ Add Plot" later, the new layer appears in Hierarchy tab with empty state guiding them through setup. No re-wizard. ## Constraints - Snapshot diffs (legacy + multiphase + areaprogram) must all stay exit 0. No calc changes. - Migrator handles old projects: existing projects without wizard preference flags get default "show all layers" behavior (current behavior preserved). - FAST cells throughout wizard. - Light + dark mode both work. - Keyboard navigable (Tab through fields, Enter advances steps). - Esc closes wizard with confirmation if any data entered. - Wizard state preserved if user goes Back to previous step. ## Verification 1. Snapshot diffs exit 0 (all 3 tracks) 2. Type-check + build pass per commit 3. Playwright headless test in `tests/e2e/m18-wizard.spec.ts`: - Create project via wizard with default mixed-use selections - Verify project landed on Area Program tab - Verify Hierarchy tab shows 3 assets - Verify Master Holding layer hidden - Test "Enable Master Holding" reveals layer - Test "+ Add Phase" creates Phase 2 - Screenshots saved to `tests/screenshots/M1.8/` for light + dark 4. `scripts/verify-m18.ts`: - Wizard completion creates expected DB rows - Default asset configs match project type matrix above - Existing projects load unchanged ## Commit Plan Split into 6-8 commits: 1. Wizard component scaffold + 3-step state machine 2. Step 1: Project Basics form 3. Step 2: Structure questions with conditional fields 4. Step 3: Asset list with project-type defaults 5. Create-project transactional handler (creates SP + Phase + Plot + Assets + Sub-Units atomically) 6. Hierarchy tab progressive disclosure (hide unused layers) 7. Hierarchy tab "+ Add Phase / Plot / Enable Master Holding" actions 8. Verification scripts + Playwright + screenshots Per-commit cadence: snapshot diff exit 0, type-check + build pass, push to main. When done, report: commit hashes, files touched per commit, verify-m18.ts output, Playwright screenshots path, pattern decisions, deviations. Begin Phase M1.8. | Done | 2026-05-03 | 2026-05-03
M2.1 | Module 2 Revenue, Sell stream |  | Not started | 0 | 0
M2.2 | Module 2 Revenue, Operate stream (USAH) | ## Purpose | Not started | 0 | 0
M2.3 | Module 2 Revenue, Lease stream |  | Not started | 0 | 0
M2.4 | Module 2 Revenue, Hybrid composition | Replace the current "blank Hierarchy tab" first experience with a guided wizard that asks 3-5 simple questions and pre-creates the project structure. User lands in a populated workspace, not an empty 5-layer tree. | Not started | 0 | 0
M2.5 | Module 2 UI tabs |  | Not started | 0 | 0
M2.6 | Module 2 snapshot guard | ## Problem We Are Solving | Not started | 0 | 0
M3 | Module 3, Operating Expenses |  | Not started | 0 | 0
M4.1 | Module 4, Project IRR / Equity IRR | Current flow: user creates project, lands on Hierarchy tab, sees 5 empty layers (Master Holding, Sub-Project, Phase, Plot, Asset, Sub-Unit), feels overwhelmed. | Not started | 0 | 0
M4.2 | Module 4, FCFE + DDM dual returns |  | Not started | 0 | 0
M4.3 | Module 4, NPV, MOIC, Payback, Margins | New flow: user answers 3 questions during creation, lands in pre-populated workspace with structure already matching their needs. 90% of users (single project, single phase, single plot, 2-3 assets) never see Master Holding or multi-plot complexity unless they explicitly opt in later. | Not started | 0 | 0
M4.4 | Module 4, DSCR, ICR, LTC, LTV |  | Not started | 0 | 0
M4.5 | Module 4, Terminal Value | ## Reference | Not started | 0 | 0
M5.1 | Module 5, P&L Statement |  | Not started | 0 | 0
M5.2 | Module 5, Cash Flow Statement | Read REFM_Build_Prompts_v2.1.xlsx Architecture sheet sections 1, 1A, 2 before starting. | Not started | 0 | 0
M5.3 | Module 5, Balance Sheet |  | Not started | 0 | 0
M5.4 | Module 5, Cash Sweep Waterfall | ## Target Outcome | Not started | 0 | 0
M6 | Module 6, Reports & Visualizations |  | Not started | 0 | 0
M7.1 | Module 7, Scenario engine | ### 1. Replace current "+ New Project" button behavior | Not started | 0 | 0
M7.2 | Module 7, Sensitivity tables |  | Not started | 0 | 0
M7.3 | Module 7, Breakeven analysis | Currently the New Project button in Projects screen creates an empty project and routes to Hierarchy tab. Change it to open a 3-step wizard modal. | Not started | 0 | 0
M8.1 | Module 8, Portfolio rollup |  | Not started | 0 | 0
M8.2 | Module 8, Cross-project allocation | ### 2. Wizard Step 1: Project Basics | Not started | 0 | 0
M9.1 | Module 9, Research agent |  | Not started | 0 | 0
M9.2 | Module 9, Market Rates agent | Inputs: | Not started | 0 | 0
M9.3 | Module 9, Agent UI integration | #NAME? | Not started | 0 | 0
M11.1 | Module 11, Final Dashboard layout | - Location (required, e.g., "Riyadh, Saudi Arabia") | Optional v1.5 | 0 | 0
M11.2 | Module 11, Charts package | #NAME? | Not started | 0 | 0
M11.3 | Module 11, Live scenario switcher | - Model Type (radio: Annual / Monthly, default Annual) | Not started | 0 | 0
M12.1 | Module 12, IM PDF builder | - Project Start Date (default today + 6 months) | Not started | 0 | 0
M12.2 | Module 12, IM PPT builder | - Status (radio: Draft / Active, default Draft) | Not started | 0 | 0
M13.1 | Module 13, Excel formula export (Enterprise) |  | Not started | 0 | 0
M13.2 | Module 13, PDF Whitelabel (Enterprise) | Validation: Name and location required. Show "Continue" disabled until both filled. | Not started | 0 | 0
Q1 | Integration QA, Hospitality fixture |  | Not started | 0 | 0
Q2 | Integration QA, MAAD fixture | ### 3. Wizard Step 2: Project Structure | Not started | 0 | 0
Q3 | Integration QA, Alma fixture |  | Not started | 0 | 0
Q4 | End-to-end snapshot guards | Three questions with smart defaults: | Not started | 0 | 0
L1 | Pre-launch hardening |  | Not started | 0 | 0
L2 | Pricing tier integration | **Question 1: Is this part of a fund or portfolio?** | Not started | 0 | 0
L3 | Launch | #NAME? | Not started | 0 | 0
- If ON: enables Master Holding layer in Hierarchy tab. If OFF: Master Holding hidden by default (user can enable later from Hierarchy tab).
**Question 2: How many phases?**
- Radio: "Single Phase (most projects)" / "Multiple Phases (staged development)"
- Default: Single Phase
- If Multiple: ask "How many?" with number input (2-10).
**Question 3: How many plots?**
- Radio: "Single Plot" / "Multiple Plots (large land bank)"
- Default: Single Plot
- If Multiple: ask "How many?" with number input (2-20).
### 4. Wizard Step 3: Assets
Based on user's project type selection, pre-fill suggested assets.
**First, ask Project Type:**
#NAME?
#NAME?
**Then suggest assets based on type:**
¦ Project Type ¦ Default Assets ¦
¦--------------¦----------------¦
¦ Residential ¦ 1 asset: "Residential Tower" (High-end Apartments, Sell, 100%) ¦
¦ Hospitality ¦ 1 asset: "Hotel" (Hotel 5-star, Operate, 100%) ¦
¦ Retail ¦ 1 asset: "Retail Center" (Retail, Lease, 100%) ¦
¦ Office ¦ 1 asset: "Office Tower" (Office, Lease, 100%) ¦
¦ Mixed-Use ¦ 3 assets: Residential Tower (Sell, 50%), Hotel (Operate, 30%), Retail Podium (Lease, 20%) ¦
¦ Custom ¦ Empty list, user adds manually ¦
User can edit/add/remove assets in this step.
For each asset row:
#NAME?
- Type dropdown (20 pre-built + Custom option)
- Category (auto-derived from type, or user-set if Custom)
- Allocation % (auto-balances to 100 across all assets)
- Remove button (if more than 1 asset)
- "+ Add Asset" button below
Validation: Total allocation must = 100%. Show "Create Project" disabled until valid.
### 5. On "Create Project"
Create the project with:
- Sub-Project: "Main" (or user-named in Step 1)
- Phase 1 (and Phase 2, Phase 3 if user picked Multiple Phases)
- Plot 1 (and Plot 2... if user picked Multiple Plots)
- Assets pre-created per Step 3 list, all bound to Phase 1 + Plot 1 by default
- Single sub-unit per asset auto-created with placeholder values:
- Sell: 1 unit, Unit Size = 100 sqm, Price = 0 (user fills later)
- Operate: 1 key/unit, quantity = 1 (user fills later)
- Lease: 1 area unit, area = 0 (user fills later)
- Master Holding: NOT created unless Step 2 Question 1 was ON
- Routes to Area Program tab (not Hierarchy tab) since structure is already set up
### 6. Hierarchy Tab Polish
When Hierarchy tab is opened on a wizard-created project:
- Hide layers user said they don't need (Master Holding, multi-phase complexity, multi-plot complexity)
#NAME?
- Top of Hierarchy tab: 3 action buttons always visible
- "+ Add Phase" (creates Phase 2, etc.)
- "+ Add Plot" (creates Plot 2, etc.)
- "Enable Master Holding" toggle (turns on the Master Holding layer if user wants to convert to fund structure later)
### 7. Edit Project Structure Later
When user clicks "Enable Master Holding" or "+ Add Phase" or "+ Add Plot" later, the new layer appears in Hierarchy tab with empty state guiding them through setup. No re-wizard.
## Constraints
- Snapshot diffs (legacy + multiphase + areaprogram) must all stay exit 0. No calc changes.
- Migrator handles old projects: existing projects without wizard preference flags get default "show all layers" behavior (current behavior preserved).
#NAME?
- Light + dark mode both work.
- Keyboard navigable (Tab through fields, Enter advances steps).
- Esc closes wizard with confirmation if any data entered.
- Wizard state preserved if user goes Back to previous step.
## Verification
1. Snapshot diffs exit 0 (all 3 tracks)
2. Type-check + build pass per commit
3. Playwright headless test in `tests/e2e/m18-wizard.spec.ts`:
- Create project via wizard with default mixed-use selections
- Verify project landed on Area Program tab
- Verify Hierarchy tab shows 3 assets
- Verify Master Holding layer hidden
- Test "Enable Master Holding" reveals layer
- Test "+ Add Phase" creates Phase 2
- Screenshots saved to `tests/screenshots/M1.8/` for light + dark
4. `scripts/verify-m18.ts`:
- Wizard completion creates expected DB rows
- Default asset configs match project type matrix above
- Existing projects load unchanged
## Commit Plan
Split into 6-8 commits:
1. Wizard component scaffold + 3-step state machine
2. Step 1: Project Basics form
3. Step 2: Structure questions with conditional fields
4. Step 3: Asset list with project-type defaults
5. Create-project transactional handler (creates SP + Phase + Plot + Assets + Sub-Units atomically)
6. Hierarchy tab progressive disclosure (hide unused layers)
7. Hierarchy tab "+ Add Phase / Plot / Enable Master Holding" actions
8. Verification scripts + Playwright + screenshots
Per-commit cadence: snapshot diff exit 0, type-check + build pass, push to main.
When done, report: commit hashes, files touched per commit, verify-m18.ts output, Playwright screenshots path, pattern decisions, deviations.
Begin Phase M1.8.

## Backlog
REFM Platform: Backlog
Polish, UX, and post-MVP items. Picked up after required modules ship.
# | ID | Item | Description | Priority | Hours | When
1 | B1 | Sample Project template | Pre-built MAAD-like and Project West-like demo projects. New user clicks 'Try Sample' instead of 'New Project', lands in fully-populated dashboard with all numbers, charts, scenarios visible immediately. Drops 'wow' factor for first-time users. | High | 6 | After Module 11
2 | B2 | Module unlock progressive reveal | As each Module ships through M2 to M11, remove SOON badge from sidebar. By launch, no SOON-locked modules visible. Avoids first impression of 'platform full of locks'. | Medium |  | Ongoing during build
3 | B3 | First-time empty state push verification | Re-eyeball Hierarchy tab Quick Setup vs Manual Setup balance after Modules 2 to 11 ship. If users bounce on empty Hierarchy tree, polish the empty state to push Quick Setup harder. | Medium | 4 | After Module 11
4 | B4 | Module 11 Final Dashboard polish budget | Reserve extra polish time on M11.1 to M11.3. Final Dashboard is the wow moment of the platform: live KPIs, scenario toggle, charts. Invest more here than other modules. Add micro-interactions, transitions, color-graded conditional formatting. | High | 8 | M11.1 to M11.3 phase
5 | B5 | Project name editing UI nicety | From Phase 4.3 backlog. Currently project name set at creation, edit pencil added in M1.5. Verify edit affordance is discoverable and not buried. | Low | 2 | Pre-launch L1
6 | B6 | User guide and documentation | Was L1.1. Static /docs/refm-getting-started page covering 5-layer hierarchy with diagram, Quick Setup walkthrough, FAST cell convention legend, scenario system intro, exporting models. Linked from Hierarchy tab and sidebar. | Medium | 8 | Pre-launch L1
7 | B7 | Cookie scope cross-subdomain fix | From Phase 4 known issue. NextAuth cookies.sessionToken.options.domain set to .financialmodelerpro.com so portal and modeling hub share session across subdomains. Required if user data ever needs to flow between hubs. | Low | 2 | If cross-subdomain feature needed
8 | B8 | REFM workspace tooltip layer | Tooltips on key terms across all modules: FAR, BUA, GFA, DSCR, IRR, MOIC, NPV, USAH, FCFE, DDM, etc. Hover any acronym to see plain-English explanation. Reduces friction for non-finance users. | Medium | 6 | Pre-launch L1
9 | B9 | Stale floating rate reminder | From MAAD model review. SAIBOR + premium model is static input. Floating rate sensitivity not modeled. Add as v2 feature when needed by users with floating-rate construction loans. | Low | 8 | v2 post-launch
10 | B10 | Multi-currency support | From Architecture decision section 3. Single currency per project for v1. Multi-currency (e.g., USD loan inside SAR project) deferred to v2 if institutional users request it. | Low | 12 | v2 post-launch
11 | B11 | Securitization mode | From Architecture decision section 1. Out of scope for v1 per Ahmad. Add later if user base requests. | Low | 16 | v2 post-launch
12 | B12 | Floating interest rate engine | From Architecture decision section 5. Fixed rate per tranche for v1. SAIBOR + premium floating rate option deferred to v2. | Low | 8 | v2 post-launch
13 | B13 | In-app interactive Investment Memorandum | From Architecture decision section 10. v1 ships PDF + PPT export of IM. Interactive in-app IM view (live tables, drill-downs) deferred to v2. | Low | 16 | v2 post-launch
14 | B14 | Authenticated API path Playwright tests | From M1.6 verification gap. Current verify-m16.ts tests 401 gates but not authed happy path because NextAuth session cookie minting is browser-only. Add full E2E with Playwright session injection. | Medium | 4 | Pre-launch L1
15 | B15 | Module 1 hierarchy onboarding video | 30 to 60 second video walkthrough of 5-layer hierarchy. Embedded in Hierarchy tab empty state. Optional viewing. | Low | 4 | Pre-launch L1